## Example improvement and impleme
Example improvement and implementation plan
This is an example improvement and implentation plan with contributing outcome A1.a and A1.b completed.
The plan is based on the recommendations and prioritisation provided as part of the assurance process. Ultimately, it is up to your council to define the ownership/roles and how to most effectively measure the required cost and effort to implement each recommendation.
About the implementation priority column
Implementation timelines for the recommendations will be determined by the council based on available investment and resources. For the purposes of this plan, the timeline has been split into four quarters (Q1 to Q4) to cover a 12-month period. When this period starts is up to your council.
Implementation priority | Timeline expectations
High | Commence Q1 and to target delivery no later than end of Q2
Medium rating | Target completion Q3/Q4
Low rating | Target completion within 2026, or at a later stage by 2030
No action | Recommendation(s) will not be implemented. The council accepts the risk of not taking action.
|  |  |  | Step 1: Review recommendations from assurer |  |  |  | Step 2: Complete implementation plan
Objective | Principle | Recommendation theme | Contributing outcome | Recommendation | Risk Level | Description of risk | Control types (People / Process / Technology) | Ownership / Roles Responsible | Cost | Effort | Complexity | Implementation justification | Implementation priority | Quarter 1 (Starts: 01/25) | Quarter 2 (Starts: 04/25) | Quarter 3 (Starts: 07/25) | Quarter 4 (Starts: 10/25) | Next year (Starts: 01/26)
A - Managing security risk | A1 - Governance | The organisation has appropriate management policies, processes and procedures in place to govern its approach to the security of network and information systems. | A1.a - Board direction | R1. The Council should form an Information Security working group. This initiative has already identified, and the group should involve the Senior Governance Officer, System Support and System Admins. R2. Ensure that security of the network and information systems is a regular topic at board-level by providing monthly reports to be discussed at Board level. | Medium | Lack of structured oversight and communication of cyber security topics at Board level could lead to insufficient risk management, lack of executive awareness, ineffective decision-making, reduced organisational resilience, and reputional damage. | People, Process | Senior Leadership Team (SLT) SIRO IT and Cyber Teams | 5 days of effort | Low | Medium | This recommendation has been prioritised due to risk level and the relatively low cost and effort required to be implemented. | High
|  |  | A1.b - Roles and responsibilities | R3. The Council should create, document and implement a process for reviewing roles and responsibilities, including defining a RACI. R4. Roles and responsibilities should be clearly communicated to senior managers. | Medium | Lack of defined, documented and communicated roles and responsibilities, including documented RACI, exposes the Council to risks such as unclear accountability, inefficient operations, and potential overlap or gaps in job functions. This lack of clarity and formalised review process can lead to miscommunication, reduced operational effectiveness, and increased chances of critical tasks being overlooked or duplicated. | People, Process | SIRO Service Lead IT and Cyber Teams | 3 days of effort | Low | Medium | This recommendation will be implemented as part of the next Q2/Q3 as additional roles and responsibilities will be defined within the current period. | Medium
|  |  | A1.c - Decision making | R5. Continue to formalise the corporate risk management framework and policy and set the risk appetite. Ensure this is implemented at Directorate level and supported by more focused risk management and registers. | Medium | Lack of formally defined corporate risk management framework and policy, including a defined and documented risk appetite, could lead to inconsistent risk management practices, unclear risk tolerance, and inadequate identification and mitigation of risks across different departments. Without a formalised framework and policy, the Council may not be able o prioritise risks appropriately, leading to delayed responses to emerging threats, increased vulnerability to unexpected events, and potential non-compliances with regulatory requirements. | People, Process | N/A | N/A | Select effort level | Select complexity level | This recommendation has already been actioned by the council and is currently underway due to be completed within the current Quarter, so no further action is required. | No action
| A2 - Risk management | The organisation takes appropriate steps to identify, assess and understand security risks to the network and information systems supporting the operation of essential functions. This includes an overall organisational approach to risk management. | A2.a - Risk management process |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | A2.b - Assurance |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| A3 - Asset management | Everything required to deliver, maintain or support networks and information systems necessary for the operation of essential functions is determined and understood. This includes data, people and systems, as well as any supporting infrastructure (such as power or cooling). | A3.a - Asset management
| A4 - Supply chain | The organisation understands and manages security risks to networks and information systems supporting the operation of essential functions that arise as a result of dependencies on external suppliers. This includes ensuring that appropriate measures are employed where third party services are used. | A4.a - Supply chain
D - Minimising the impact of cyber security incidents | D1 - Response and recovery planning | There are well-defined and tested incident management processes in place, that aim to ensure continuity of essential functions in the event of system or service failure. Mitigation activities designed to contain or limit the impact of compromise are also in place. | D1.a - Response plan |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | D1.b - Response and recovery capability |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | D1.c - Testing and exercising |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| D2 - Lessons learned | When an incident occurs, steps must be taken to understand its root causes and ensure appropriate remediating action is taken. | D2.a - Incident root cause analysis |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level