## Example plan
Example improvement and implementation plan
[OFFICIAL - SENSITIVE] Please do not share this externally.
This is an example improvement and implementation plan with contributing outcomes B1.a and B1.b completed.
The plan is based on the recommendations and prioritisation provided as part of the assurance process. Ultimately, it is up to the individual council to define the ownership/roles and how to most effectively measure the required cost and effort to implement each recommendation.
About the implementation priority column
Implementation timelines for the recommendations will be determined by the council based on available investment and resources. For the purposes of this plan, the timeline has been split into four quarters (Q1 to Q4) to cover a 12-month period. When this period starts is up to you.
Implementation priority | Timeline expectations
High | Commence Q1 and to target delivery no later than end of Q2
Medium rating | Target completion Q3/Q4
Low rating | Target completion within 2025, or at a later stage by 2030
No action | Recommendation(s) will not be implemented. The council accepts the risk of not taking action.
|  |  |  | Step1: Review recommendations |  |  |  | Step 2: Complete implementation plan
Objective | Principle | Recommendation theme | Contributing outcome | Recommendation | Risk Level | Description of risk | Control types (People / Process / Technology) | Ownership / Roles responsible | Cost | Effort | Complexity | Implementation justification | Implementation priority | Quarter 1 (MM/YY) | Quarter 2 (MM/YY) | Quarter 3 (MM/YY) | Quarter 4 (MM/YY) | Next year (Starts MM/YY)
B - Protecting against cyber attack | B1 - Service protection policies, processes and procedures | The organisation defines, implements, communicates and enforces appropriate policies, processes and procedures that direct its overall approach to securing systems and data that support the operation of essential functions. | B1.a - Policy and process development | R1 - Ensure cyber security policies and standards are fully embedded in all processes and systems supporting essential functions. R2 - A full review of relevant existing policies should be performed, and a schedule put in place for future reviews. The review should also be used to identify missing or incomplete policies that should be created or finished accordingly. | High | Failure to fully embed and regularly review cybersecurity policies across essential functions can lead to inconsistent security practices, increasing the risk of vulnerabilities such as unauthorised access, data breaches, and system disruptions. Outdated, missing, or incomplete policies may leave critical systems exposed to evolving cyber threats and regulatory non-compliance. Without a structured review process, the Council may struggle to adapt to emerging risks, leading to potential financial, operational, and reputational damage. | Process | SIRO IT and Cyber Teams | 5 days effort | Medium | Low | This recommendation has been prioritised due to risk level and the relatively low cost and effort required to be implemented | High
|  |  | B1.b - Policy and process implementation | R3 - The Council needs to develop and implement mechanisms for validating user compliance to information security policies, and ensure compliance baselines are set. R4 - Policies and processes should be centrally stored and managed, allowing for the effective communication of policies and procedures to all users. | Medium | Without mechanisms to validate user compliance and centrally manage security policies, there is an increased risk of inconsistent adherence to protocols, exposing the Council to data breaches, unauthorised access, and regulatory non-compliance. Poor communication of policies can further lead to security gaps and operational inefficiencies. | Process, Technology | SIRO Service Lead IT and Cyber Teams | 15 days effort | Medium | Medium | This recommendation will be implemented as part of the next Q2/Q3 as additional as a tool to centrally manage policies and processes is planned to be purchased within the current period | Medium
| B2 - Identity access and control | The organisation understands, documents and manages access to networks and information systems and supporting the operation of essential functions. Users (or automated functions) that can access data or services are appropriately verified, authenticated and authorised. | B2.a - Identity verification, authentication and authorisation |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B2.b - Device management | [6 empty] | Select effort level | Select complexity level |  | Select priority level
|  |  | B2.c - Privileged user management |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B2.d - Identity and Access Management (IdAM) |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| B3 - Data security | Data stored or transmitted electronically is protected from actions such as unauthorised access, modification, or deletion that may cause an adverse impact on essential functions. Such protection extends to the means by which authorised users, devices and systems access critical data necessary for the operation of essential functions. It also covers information that would assist an attacker, such as design details of networks and information systems. | B3.a - Understanding data |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B3.b - Data in transit |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B3.c - Stored data |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B3.d - Mobile data |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B3.e - Media / equipment sanitisation |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| B4 - System security | Network and information systems and technology critical for the operation of essential functions are protected from cyber attack. An organisational understanding of risk to essential functions informs the use of robust and reliable protective security measures to effectively limit opportunities for attackers to compromise networks and systems. | B4.a - Secure by design |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B4.b - Secure configuration |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B4.c - Secure management |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B4.d - Vulnerability management |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| B5 - Resilient networks and systems | The organisation builds resilience against cyber attack into the design, implementation, operation and management of systems that support the operation of essential functions. | B5.a - Resilience preparation |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B5.b - Design for resilience |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B5.c - Backups |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| B6 - Staff awareness and training | Staff have appropriate awareness, knowledge and skills to carry out their organisational roles effectively in relation to the security of network and information systems supporting the operation of essential functions. | B6.a - Cyber security culture |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | B6.b - Cyber security training |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
C - Detecting cyber security events | C1 - Security monitoring | The organisation monitors the security status of the network and information systems supporting the operation of essential functions in order to detect potential security problems and to track the ongoing effectiveness of protective security measures. | C1.a - Monitoring coverage |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | C1.b - Securing logs |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | C1.c - Generating alerts |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | C1.d - Identifying security incidents |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | C1.e - Monitoring tools and skills |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
| C2 - Proactive security event discovery | The organisation detects, within networks and information systems, malicious activity affecting, or with the potential to affect, the operation of essential functions even when the activity evades standard signature based security prevent/detect solutions (or when standard solutions are not deployable). | C2.a - System abnormalities for attack detection |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level
|  |  | C2.b - Proactive attack discovery |  | Select risk level |  |  |  |  | Select effort level | Select complexity level |  | Select priority level

## Recomendations Share with counc (hidden)
Complete and share with council
Recommendations on how to meet the contributing outcomes
[OFFICIAL SENSITIVE] Please do not share this profile externally.
The table below shows the assesor's recomendations for each outcome. Each recommendation has a suggested priority rating to help you focus your efforts.
What the priority ratings mean
Priority rating | Description
High | What high means
Medium | What medium means
Low | What low means
Objective | Principle | Contributing outcome | What councils should aim to achieve | How the council assessed its own status | How the assessor assessed the council | Local CAF Profile Met | Recommendations | Risk | Priority
A - Managing security risk | A1 - Governance | A1.a - Board direction | Achieved | Achieved | Not Achieved | No | R1 - R2 - |  | High
|  | A1.b - Roles and responsibilities | Achieved | Achieved | Not Achieved | No | R3 - |  | Medium
|  | A1.c - Decision making | Achieved | Achieved | Not Achieved | No | R4 - |  | Medium
| A2 - Risk management | A2.a - Risk management process | Partially achieved | Partially achieved | Partially achieved | Yes
|  | A2.b - Assurance | Achieved | Achieved | Achieved | Yes
| A3 - Asset management | A3.a - Asset management | Achieved | Achieved | Achieved | Yes
| A4 - Supply chain | A4.a - Supply chain | Partially achieved | Partially achieved | Partially achieved | Yes
D - Minimising the impact of cyber security incidents | D1 - Response and recovery planning | D1.a - Response plan | Achieved | Achieved | Achieved | Yes
|  | D1.b - Response and recovery capability | Achieved | Achieved | Achieved | Yes
|  | D1.c - Testing and exercising | Achieved | Achieved | Achieved | Yes
| D2 - Lessons learned | D2.a - Incident root cause analysis | Achieved | Achieved | Achieved | Yes
|  | D2.b - Using incidents to drive improvements | Achieved | Achieved | Achieved | Yes