## Index
This document is an example showing what a completed version of the Secure by Design self assessment tracker might look like. This worksheet is the index you can use to navigate to individual sheets. Index begins in cell A2. Note: Rows and columns outside of the tables are hidden to prevent accidental navigation. There's guidance on how to use the tracker on the Tracking Secure by Design progress page.
Index
Project profile
Discovery
Alpha
Private beta
Public beta or live
Release notes

## Project profile
Project profile data worksheet. This worksheet includes three tables: 1. Project details, beginning in cell A3, with empty cells in column B to add data. 2. Confidence profile history, beginning in cell D3. Data is dynamic and automated. 3. Document control, beginning in cell D9, with empty cells in column E to add data.
Secure by Design: Self assessment tracker (beta v1.1)
How to complete the tracker: Tracking Secure by Design progress
Project dashboard | Details | The tracker starts at a 'Low' confidence status by default. The confidence status increases to 'Medium' or 'High' based on the responses you provide.
Government organisation or arm's-length body (ALB) | Department of Artificial Intelligence and Robotic Technologies (DAIRT)
Project name | Grant Management Service | Confidence profile dashboard | Status
Overview or scope | The GMS will manage grants available to SME businesses and sole traders working within the AI and robotics fields. For full details, see Overview.docx | Discovery | High
Project manager or delivery manager | Kafui | Alpha | High
Senior Responsible Owner (SRO) | Berni | Private beta | High
Security architect | Bob | Public beta or live | Low
Technical architect | Oliver
Security subject matter expert | Remesh | Document control dashboard | Details
Technical subject matter expert | Liadi | Document classification | OFFICIAL - SENSITIVE
Start date | 2025-05-27 | Completed by | Fotini
Go live date | 2025-11-30 | Version number | 0.1
Delivery phase | Private beta or Design-build-test-implement | Last updated on | 2025-09-10
Delivery phase (if using non-agile methodology) |  | Date of last assurance review | TBC

## Discovery
Discovery phase worksheet. This table contains actions 1 to 39. The table begins in cell A2. Rows 1, 2 and 3 are frozen. The table direction is left to right.
Confidence status: | High | Congratulations! This project has achieved the required confidence score.
Reference | Questions | Response | Notes or evidence | Response score
Considering security within the business case will help you meet principles 1, 2, 3, 4 and 9
Action 1 | Have you consulted relevant security stakeholders when developing your business case? | Yes | We consulted the internal cyber security team and information assurance leads during early-stage scoping to ensure security alignment with strategic goals. | 1
Action 2 | Does the business case include cyber security considerations? | Yes | The business case outlines the need for Secure by Design and includes security as a key delivery enabler. Refer to the Strategic Outline Case. | 1
Action 3 | Does the economic case include an analysis with the security threats, security risk tolerance, security objectives and cyber resilience as part of critical success factors? | No | We have not yet embedded threat modelling or cyber resilience metrics into the economic case. | 0
Action 4 | Does the economic case consider varying levels of security when calculating value for money? | Yes | We assessed security cost and benefit at different assurance levels to inform decision-making. | 1
Action 5 | Does the management case include details of the security governance and assurance approach? | Yes | Security roles and decision-making are described in the delivery governance model. | 1
Identifying security resources will help you meet principle 1 |  |  |  | 7.6596
Action 6 | Does the project have a resource plan showing security roles and skills required to support the delivery of the service? | Yes | Yes, this includes service owner, user researcher, service designer, business analyst and cyber security professional. These are consistent with guidance in the Service Manual section, The team. | 1
Action 7 | Have you identified and captured the skills required to carry out security activities and engaged with your organisation's security team to support the delivery? | Yes | We engaged with the internal risk team to confirm the skillsets required and secured specialist input. | 1
Action 8 | Have you identified and captured the required technology resources such as software development environments, tools and security capabilities that will be required for the project? | Yes | We have identified the necessary technology resources, including the chosen Software as a Service (SaaS) platform, development tools and key security capabilities. These are regularly reviewed to ensure alignment with Secure by Design principles throughout the project. | 1
Action 9 | Have you considered pre-approved or recommended architectural patterns available from your organisation or other government departments? | Yes | The NCSC cloud security principles, pre-approved architectural patterns for SaaS solutions, including guidance on secure configuration, identity and access controls, data protection, and integration with government-approved security services | 1
Agreeing roles and responsibilities will help you meet principle 1 |  |  |  | 7.4468
Action 10 | Have you assigned the Secure by Design responsibilities (for example, in a RACI matrix) and communicated them to the relevant parties? | Yes | Refer to the document Grant Applications Service RACI.xls | 1
Action 11 | Have you appointed a Senior Responsible Owner (SRO), service owner or equivalent, and informed the individual of their responsibilities? | Yes | The service owner is NAME. They have accepted accountability and are actively engaged in governance. | 1
Tracking Secure by Design progress will help you meet principle 9 |  |  |  | 8.5106
Action 12 | Have you included continuous assurance processes in the service's project delivery workflow? | Yes | We have considered all Secure by Design activities for discovery as recommended in the How to integrate Secure by Design into the government gate review life cycle guidance. We've added these to the backlog and created epics for each, which span a number of sprints. | 1
Working out the project’s security risk appetite will help you meet principles 3 and 9 |  |  |  | 10.6383
Action 13 | Have you used the organisation's risk appetite statements and applied them to the nature of the service to determine the security risk appetite level for the project? | Yes | The project aligns to our baseline risk tolerance defined by corporate security policy. See our risk appetite statement. | 1
Action 14 | Have you established a clear governance structure around risk management decision making? | No | We are still refining escalation routes for risk acceptance and mitigation decisions. | 0
Action 15 | Have you considered the risk appetite of any organisations the service shares or exchanges data with? | No | We have not yet reviewed HMRC’s or partner departments’ risk postures. | 0
Action 16 | Have you considered whether the service is part of the Critical National Infrastructure (CNI) or fundamental to the organisation's output and missions? | Yes | This service is not categorised as CNI but is essential for departmental grant delivery. | 1
Action 17 | Have you considered the appropriate Cyber Assessment Framework (CAF) profile for all the components of the service? | Yes | We applied the CAF basic profile to guide assurance activities. | 1
Managing third-party product security risks will help you meet principle 2 |  |  |  | 5.7447
Action 18 | Have you reviewed the security risks of any cloud technology (such as IaaS, PaaS, SaaS) before using it? | N/A | The project is in the early procurement phase. We will conduct security risk assessments once the SaaS provider shortlist is confirmed. | N/A
Action 19 | Have you identified the security risks related to third-party Managed Service Providers (MSPs) prior to using them? | N/A | No MSP has been contracted yet. We will assess risks during commercial evaluation. | N/A
Action 20 | Have you assessed and managed the risks associated with any third-party development environments or software prior to committing to using them? | N/A | We have not yet committed to any external development environment. Assessment will follow selection. | N/A
Action 21 | Have you created a report that highlights any security risks associated with using third-party products, including recommendations on how to manage those risks? | No | We have not yet documented this. It will be completed following supplier selection. | 0
Understanding cyber security obligations will help you meet principles 3 and 9 |  |  |  | 0
Action 22 | Have you discussed security obligations, including government policies, regulations, laws and contracts, for your service with your organisation's compliance or information security teams? | Yes | We have reviewed DPA 2018, UK GDPR, FoIA, Managing Public Money and PCI-DSS with the compliance and cyber teams. | 1
Action 23 | Have you fed compliance requirements into risk management activities? | No | This activity is outstanding. We will incorporate legal and regulatory obligations into our project-level risk assessment activities. | 0
Action 24 | Have you met obligations in relation to personally identifiable information (PII) being processed, stored or transmitted by the service? | Yes | The DPIA addresses handling of PII and aligns with DPA 2018 and UK GDPR requirements. | 1
Action 25 | Have you met obligations in relation to financial information (such as credit card details) being processed, stored or transmitted by the service? | Yes | The service design will incorporate PCI/DSS compliance controls for any payment processing. | 1
Action 26 | Have you met obligations in relation to intellectual property (IP) data being processed, stored or transmitted by the service? | Yes | We have reviewed obligations under the Copyright, Designs and Patents Act to ensure compliance. | 1
Action 27 | Have you documented the legal, regulatory and contractual requirements that must be met by the service? | Yes | We maintain a list of obligations including Public Contracts Regulations and sector-specific duties. | 1
Action 28 | Have you ensured that other organisations you plan to share data with as part of the service delivery are compliant with the relevant cyber security obligations? | No | This is in progress; we are reviewing HMRC and third-party compliance postures. | 0
Action 29 | Have you defined data sharing agreements with any organisations you are sharing data with? | Yes | We have a Memorandum of Understanding (MoU) in development with HMRC for data sharing. | 1
Action 30 | If data will be processed, stored or transmitted outside the UK or the European Economic Area (EEA), have you considered the relevant security obligations? | N/A | All data will be stored and processed within the UK sovereign cloud. | N/A
Action 31 | Have you completed a Data Protection and Impact Assessment (DPIA)? | Yes | Refer to DPA_Grant_Management_Service.docx. | 1
Understanding business objectives and user needs will help you meet principle 4 |  |  |  | 6.6194
Action 32 | Have you taken business objectives into account when making security decisions? | Yes | Security objectives directly align with our core delivery goals around public trust and efficient service. | 1
Action 33 | Have you taken user needs into account when making security decisions? | Yes | User research informed decisions such as use of multi-factor authentication (MFA) and secure account access. | 1
Documenting service assets will help you meet principles 3 and 7 |  |  |  | 9.5745
Action 34 | Have you identified and documented the business and technology information assets in scope of the service? | Yes | We maintain an asset register covering all business and technical components. Refer to Information_Asset_List.xls. | 1
Action 35 | Have you identified and documented a service owner or information asset owner for each asset? | Yes | All assets have an assigned owner for oversight and accountability. Refer to Information_Asset_List.xls. | 1
Assessing the importance of service assets will help you meet principle 3 |  |  |  | 9.5745
Action 36 | Have you completed a business impact assessment to determine the confidentiality, integrity and availability of data if the service was compromised? | No | We had a discussion but did not document anything. | 0
Action 37 | Did you consult with business stakeholders when creating the impact assessment? | Yes | We worked with the service owner, delivery lead and business sponsor during the impact assessment discussion. | 1
Sourcing a threat assessment will help you meet principle 3 |  |  |  | 4.7872
Action 38 | Have you obtained the organisation's overarching threat assessment (or completed your own if there is not one available)? | Yes | We used the organisation's existing threat model and contextualised it for this service. | 1
Action 39 | Does your threat assessment include the motives, intent and capability of the threat actors relevant to your service? | Yes | Our threat assessment includes internal misuse, organised fraud and state-level threats. | 1
Action 40 | Have you considered threat intelligence and the history of previous attacks on the organisation (or similar organisations) as part of the threat assessment? | Yes | We included historical incident data and threat intelligence reports in our review. | 1
End of worksheet |  |  |  | 10.6383
81.1939
Note on B2: The tracker starts at a 'Low' confidence status by default. The confidence status increases to 'Medium' or 'High' based on the responses you provide.
Note on B5: It is important to identify the stakeholders with an interest in the service and give them the opportunity to provide input into security elements of the business case so it reflects their needs.
Note on B6: Cyber security should be considered from the start of a project and included in the business case so sufficient resources can be secured for responding to and mitigating risks.
Note on B7: This will help support the case for necessary cyber security investment.
Note on B8: Providing the pros and cons of security approaches will help demonstrate the need for investment in security.
Note on B9: This should include the relevant governance and assurance frameworks and outline the rules and responsibilities of senior stakeholders.
Note on B11: An agreed plan with the required security skills will ensure that the security related tasks will be executed by the Suitable Qualified and Experienced Person team.
Note on B12: This will help ensure security resources are appropriately allocated throughout the delivery life cycle.
Note on B13: This will help establish what security tools will be required across the life cycle of the service.
Note on B14: This will allow the design of the service to conform to the baseline security controls embedded in established patterns, reducing the resources required to carry out cyber security activities.
Note on B16: This will provide clarity on each individual's role, identify any gaps and increase the likelihood that security activities will have appropriate governance and oversight. Refer to the indicative Secure by Design RACI Matrix.
Note on B17: This means delivery risk decisions will be made by a senior stakeholder, helping to reduce roadblocks where approval is required.
Note on B19: This will ensure a lightweight process to maintain a measure of confidence as to whether the project team is following the Secure by Design approach.
Note on B21: This allows identified security risks to be articulated, evaluated and escalated in relation to the organisation’s risk tolerance.
Note on B22: This increases the likelihood that the right protocols are followed for risks that need to be prioritised or escalated, enabling early action to be taken on priority risks.
Note on B23: This ensures the security posture of other organisations is factored in when managing security risks.
Note on B24: This will inform the security controls that you need to implement in order to meet the NCSC CAF outcomes and Indicators of Good Practice (IGP). Read more at https://www.security.gov.uk/guidance/govassure
Note on B25: This will inform the security controls that you need to implement in order to meet the NCSC CAF outcomes and Indicators of Good Practice (IGP). Read more at https://www.security.gov.uk/guidance/govassure
Note on B27: This will help identify any risks related to data sharing, access and management by third-party vendors.
Note on B28: This will highlight any security risks related to data sharing and access that need to be managed before accepting MSP contracts.
Note on B29: Security due diligence of third party technology products and vendors allows you to identify and assess any associated risks.
Note on B30: This allows you to clearly communicate identified risks to stakeholders and collaborate on mitigating or responding to them.
Note on B32: Have you discussed security obligations for your service with your organisation's compliance or information security teams?
Note on B33: This will enable compliance-related risks and appropriate remedies to be accommodated into the delivery budget and plan.
Note on B34: Seek guidance from your compliance and data protection teams on the legal implications of using PII (such as DPA and GDPR) that should be considered as part of security requirements.
Note on B35: This will ensure you meet the Payment Card Industry / Data Security Standard (PCI / DSS) and Financial Conduct Authority (FCA) regulations.
Note on B36: This will ensure you’re compliant with the relevant organisational safeguards and contractual restrictions of using IP data.
Note on B37: This will help avoid the risk of breaching law and security obligations which may result in fines or reputational damage.
Note on B38: This will help you to assess the additional security considerations that may be required when sharing data with external organisations, especially in regards to regional variations.
Note on B39: This will help to established responsibilities for data management, reducing the likelihood of mismanagement of data and allowing for processes to be agreed in the event of a data breach.
Note on B40: Seek guidance from your compliance and data protection teams on regional obligations that need to be met.
Note on B41: Carrying out a DPIA allows privacy risks to be established and the costs and timescales of remedies to be included in the delivery plan.
Note on B43: This will help security to be a business enabler with requirements developed taking into account the business needs.
Note on B44: This will help to deliver user-friendly services with proportionate security measures that create minimal friction.
Note on B46: This allows delivery teams to have an accurate picture of assets so they can support asset owners to qualify the impact to the organisation should the assets be compromised.
Note on B47: Establishing responsibility for service assets increases the likelihood they will be effectively described and understood.
Note on B49: Assessing the business impact should the confidentiality and integrity of data assets and availability of the service be compromised supports the project team in understanding the importance of the assets and in evaluating the security risks further down the line during the risk assessment activities.
Note on B50: The business stakeholders are better placed to assess the impact of a security breach of an asset. Engaging with them enables the delivery and security teams to implement security controls that are commensurate to the business impact of a breach.
Note on B52: This will give you an understanding of the threats faced by the organisation so you can assess the associated risks to your service.
Note on B53: This is essential for identifying and prioritising threats effectively so you can demonstrate that proposed risk mitigation strategies have sufficiently considered the severity of threats.
Note on B54: This is crucial for identifying emerging threats and understanding attack patterns for threat actors so risk mitigation strategies can be adjusted accordingly.

## Alpha
Alpha phase worksheet. This table contains actions 1 to 61. The table begins in cell A2. Rows 1, 2 and 3 are frozen. The table direction is left to right.
Confidence status: | High | Congratulations! This project has achieved the required confidence score.
Reference | Questions | Response | Notes or evidence | Response score
Considering security within the business case will help you meet principles 1, 2, 3, 4 and 9
Action 1 | Have you consulted relevant security stakeholders when developing your business case? | Yes | Security stakeholders were engaged during the development of the Outline Business Case. Evidence: meeting notes, stakeholder engagement log. | 1
Action 2 | Does the business case include cyber security considerations? | Yes | Cyber security considerations have been included in the Outline Business Case. Evidence: Outline_Business_Case_Gate3.pdf, section on security assumptions. | 1
Action 3 | Does the economic case include an analysis with the security threats, security risk tolerance, security objectives and cyber resilience as part of critical success factors? | No | Security threat and resilience analysis not yet incorporated into the economic case. Action: include as part of detailed options appraisal during Beta. | 0
Action 4 | Does the economic case consider varying levels of security when calculating value for money? | Yes | Economic case models include varying SaaS security levels (for example, shared vs dedicated tenancy). Evidence: cost model spreadsheet, security assumptions log. | 1
Action 5 | Does the management case include details of the security governance and assurance approach? | No | No governance or assurance structure defined in the management case. Action: draft governance model and security roles before entering beta. | 0
Identifying security resources will help you meet principle 1 |  |  |  | 3.3962
Action 6 | Does the project have a resource plan showing security roles and skills required to support the delivery of the service? | Yes | Resource plan includes dedicated security roles (for example, SaaS integration, risk/compliance SME). Evidence: Security_Resource_Plan_Alpha.xlsx. | 1
Action 7 | Have you identified and captured the skills required to carry out security activities and engaged with your organisation's security team to support the delivery? | Yes | Security skill requirements are identified; security team has been engaged. Evidence: skills matrix, team workshop notes. | 1
Action 8 | Have you identified and captured the required technology resources such as software development environments, tools and security capabilities that will be required for the project? | Yes | Technology resources (SaaS platform, SSO, dev/test tools) have been scoped. Evidence: tech stack inventory, SaaS onboarding docs. | 1
Action 9 | Have you considered pre-approved or recommended architectural patterns available from your organisation or other government departments? | No | Architectural patterns have not been reviewed. Action: consult GDS or NCSC architectural guidance in Beta. | 0
Agreeing roles and responsibilities will help you meet principle 1 |  |  |  | 3.3019
Action 10 | Have you assigned the Secure by Design responsibilities (for example, in a RACI matrix) and communicated them to the relevant parties? | Yes | Secure by Design responsibilities documented in RACI and shared with the team. Evidence: SbD_RACI_Alpha_v1.0.xlsx. | 1
Action 11 | Have you appointed a Senior Responsible Owner (SRO), service owner or equivalent, and informed the individual of their responsibilities? | Yes | Service owner (NAME) confirmed and briefed. | 1
Tracking Secure by Design progress will help you meet principle 9 |  |  |  | 5.0314
Action 12 | Have you included continuous assurance processes in the service's project delivery workflow? | Yes | We have considered all Secure by Design activities for alpha as stated in guidance and added these in the backlog and created epics for each of these which scan across a number of sprints. | 1
Working out the project’s security risk appetite will help you meet principles 3 and 9 |  |  |  | 6.2893
Action 13 | Have you used the organisation's risk appetite statements and applied them to the nature of the service to determine the security risk appetite level for the project? | Yes | Risk appetite applied using organisational guidance. Evidence: Risk_Appetite_Alignment_Memo.docx. | 1
Action 14 | Have you established a clear governance structure around risk management decision making? | No | Risk governance structure not yet finalised. Action: define risk ownership model during beta. | 0
Action 15 | Have you considered the risk appetite of any organisations the service shares or exchanges data with? | No | Data-sharing partner risk appetite not considered. Action: document this during stakeholder onboarding. | 0
Action 16 | Have you considered whether the service is part of the Critical National Infrastructure (CNI) or fundamental to the organisation's output and missions? | Yes | Service criticality assessed in discovery; aligned to organisational mission. Evidence: discovery report Service_Criticality_Review.pdf. | 1
Action 17 | Have you considered the appropriate Cyber Assessment Framework (CAF) profile for all the components of the service? | Yes | CAF profile scoped for components. Evidence: CAF_Profile_Assessment_Alpha.xlsx. | 1
Managing third-party product security risks will help you meet principle 2 |  |  |  | 3.3962
Action 18 | Have you reviewed the security risks of any cloud technology (such as IaaS, PaaS, SaaS) before using it? | Yes | SaaS platform risks reviewed against standard threat models. Evidence: Cloud_Security_Risk_Assessment_Alpha.pdf. | 1
Action 19 | Have you identified the security risks related to third-party Managed Service Providers (MSPs) before using them? | N/A | No MSP used. | N/A
Action 20 | Have you assessed and managed the risks associated with any third-party development environments or software before committing to using them? | Yes | Risks for tools (for example, GitHub, CI/CD) assessed. Evidence: ThirdParty_Security_Review_Alpha.docx. | 1
Action 21 | Have you created a report that highlights any security risks associated with using third-party products, including recommendations on how to manage those risks? | Yes | Report created outlining third-party risks and recommendations. Evidence: ThirdParty_Risk_Report_v1.0.pdf. | 1
Documenting service assets will help you meet principles 3 and 7 |  |  |  | 4.4025
Action 22 | Have you identified and documented the business and technology information assets in scope of the service? | Yes | We maintain an asset register covering all business and technical components. Refer to Information_Asset_List.xls. | 1
Action 23 | Have you identified and documented a service owner or information asset owner for each asset? | Yes | All assets have an assigned owner for oversight and accountability. Refer to Information_Asset_List.xls. | 1
Assessing the importance of service assets will help you meet principle 3 |  |  |  | 5.0314
Action 24 | Have you completed a business impact assessment to determine the confidentiality, integrity and availability of data if the service was compromised? | Yes | We completed a Business Impact Assessment (BIA) to evaluate the effect of compromised data on confidentiality, integrity and availability. Evidence: BIA_SaaS_Alpha_v1.0.xlsx. | 1
Action 25 | Did you consult with business stakeholders when creating the impact assessment? | Yes | Business stakeholders were consulted during the BIA process through interviews and workshops. Evidence: BIA_Stakeholder_Engagement_Notes.pdf. | 1
Sourcing a threat assessment will help you meet principle 3 |  |  |  | 5.0314
Action 26 | Have you obtained the organisation's overarching threat assessment (or completed your own if there is not one available)? | Yes | We used the organisation’s overarching threat assessment | 1
Action 27 | Does your threat assessment include the motives, intent and capability of the threat actors relevant to your service? | Yes | The threat assessment includes likely attacker profiles, their motives, capabilities, and attack methods relevant to a SaaS environment. Evidence: Service_Threat_Profile_SaaS_Alpha.docx. | 1
Action 28 | Have you considered threat intelligence and the history of previous attacks on the organisation (or similar organisations) as part of the threat assessment? | Yes | Threat intelligence was reviewed, including historical attacks on similar SaaS services. | 1
Performing threat modelling will help you meet principles 3 and 7 |  |  |  | 5.6604
Action 29 | Have you documented the technical architecture for the end-to-end service and system? | Yes | A technical architecture diagram of the end-to-end service has been created. Evidence: Technical_Architecture_Diagram_SaaS_Alpha.vsdx. | 1
Action 30 | Have you identified and documented the possible attack paths or threat events that could be used to exploit vulnerabilities in the service? | Yes | Potential attack paths were identified through threat modelling exercises. Evidence: Threat_Model_SaaS_Alpha.drawio.pdf. | 1
Action 31 | Have you identified and documented what security controls are available to reduce the likelihood of threat events? | Yes | Available controls were documented against each threat. Evidence: Security_Control_List_Alpha.xlsx. | 1
Action 32 | Have you identified and documented any security controls that could mitigate multiple threat events? | Yes | Cross-cutting controls (for example, SSO, logging, encryption) were identified as mitigating multiple threat scenarios | 1
Action 33 | Have you conducted a security design review against good practice principles and patterns? | No | A formal security design review has not been conducted yet. Action: Plan review session for early beta using NCSC design principles. | 0
Performing a security risk assessment will help you meet principle 3 |  |  |  | 6.2893
Action 34 | Do the scoring scales used for your service's security risk assessment align with your organisation's risk management processes? | Yes | Our risk scoring aligns with the organisation's risk tolerance matrix. | 1
Action 35 | Have you documented the risk assessment method used to perform a risk assessment? | Yes | The risk assessment method used is documented and agreed. Evidence: Risk_Assessment_Methodology_SaaS_Alpha.docx. | 1
Action 36 | Have you validated the timeliness of the threat and business impact sources? | Yes | Threat and impact sources were reviewed and validated with security and business teams. | 1
Action 37 | Have you documented the service's risks (for example in a risk register)? | Yes | The risk register has been created and is regularly updated. Evidence: SaaS_Project_Risk_Register_Alpha_v1.1.xlsx. | 1
Agreeing a security controls set for your service will help you meet principles 3 and 10 |  |  |  | 6.2893
Action 38 | Have you identified the cyber security standards that are relevant to the service? | Yes | We identified all applicable cyber security standards for this service: NIST Cybersecurity Framework and CSA Security, Trust & Assurance Registry. | 1
Action 39 | Have you agreed the security control frameworks you intend to use with your organisation’s security function? | Yes | Security control frameworks (for example, CIS Controls, ISO 27002) were agreed with the organisation’s security function. | 1
Action 40 | Have you created a security controls set relevant to your service? | Yes | A set of controls specific to this SaaS solution was documented. Evidence: SaaS_Security_Controls_Set_Alpha.xlsx. | 1
Action 41 | Does your security controls set map to the NCSC Cyber Assessment Framework (CAF)? | No | Mapping to the NCSC CAF is pending. Action: Complete mapping in beta phase. | 0
Responding to and mitigating security risks will help you meet principles 3, 4, 5, 6, 7 and 8 |  |  |  | 4.2453
Action 42 | Have you treated the risks that have a rating above the project's risk appetite? | Yes | All risks above the defined appetite have been addressed through treatment plans. Evidence: Risk_Treatment_Log_Alpha.xlsx. | 1
Action 43 | Have you documented the risk mitigations (for example in a risk treatment plan)? | Yes | Risk mitigations are recorded in a structured plan. Evidence: Risk_Treatment_Plan_SaaS_Alpha.docx. | 1
Assessing the effectiveness of security controls will help you meet principles 4, 5, 6, 7 and 8 |  |  |  | 6.2893
Action 44 | Did you select the security controls based on risk, threats and exposure? | Yes | Security controls were selected based on threat modelling and risk outcomes. Evidence: Control_Selection_Rationale.docx. | 1
Action 45 | Have you documented the selected controls? | Yes | Controls have been documented and reviewed by technical leads. | 1
Action 46 | Have you tested the controls and confirmed they're working as intended? | Yes | Controls were tested through functional test cases and manual checks. | 1
Action 47 | Have you identified any residual risks and raised them with risk owners for sign-off? | Yes | Residual risks were identified and escalated to risk owners for sign-off. | 1
Implementing a vulnerability management process will help you meet principles 5 and 9 |  |  |  | 3.1447
Action 48 | Do you have a documented approach on how to classify, prioritise and redress vulnerabilities? | Yes | We have a vulnerability management policy that outlines classification and remediation timelines. Evidence: Vulnerability_Classification_Procedure.docx. | 1
Action 49 | Do you have a documented process for identifying and responding to new vulnerabilities in your code, systems or supply chain? | Yes | A documented process is in place for identifying and addressing new vulnerabilities. Evidence: Vulnerability_Response_Process_Alpha_v1.1.docx. | 1
Discovering vulnerabilities will help you meet principles 2, 5 and 7 |  |  |  | 5.0314
Action 50 | Are you following a secure systems software development life cycle policy or process? | Yes | We are following a secure software development lifecycle (SDLC) adapted to SaaS. | 1
Action 51 | Are you conducting regular code reviews as part of the development process? | Yes | Regular peer code reviews are conducted as part of sprint deliverables. | 1
Action 52 | Are you using a manual or automated code testing method (for example, Static Application Security Testing (SAST) or Dynamic Application Security Testing (DAST))? | No | Static or dynamic code analysis (for example, SAST/DAST) has not yet been implemented. Action: Plan for inclusion in beta or private beta phase. | 0
Action 53 | Do you have a plan for carrying out penetration tests with appropriate scopes? | N/A | Penetration testing is not scheduled for alpha. This will be scoped and scheduled in beta. | N/A
Managing observability will help you meet principles 5 and 7 |  |  |  | 3.3543
Action 54 | Do you have a documented approach for what events should be logged to help identify security incidents? | N/A | Logging requirements are not yet defined in alpha. This will be captured during system hardening in beta. | N/A
Action 55 | Have you determined the tools required to log and analyse the event logs and trigger alerts? | N/A | Tools for log analysis and alerting are not finalised yet, still under evaluation. | N/A
Action 56 | Do you have a documented approach for analysing your logs and monitoring the alerts generated? | N/A | Log analysis and monitoring strategy is planned for beta alongside tool selection. | N/A
Evaluating the security impact of changes will help you meet principle 10 |  |  |  | 0
Action 57 | Does the service delivery change management process consider the impact of changes to security? | N/A | Formal change management processes are not in place in alpha. Planned for later stages. | N/A
Action 58 | Are you reflecting requested changes in the service’s threat model? | N/A | Threat model has not yet incorporated changes due to limited change scope in alpha. | N/A
Action 59 | Are you considering requested changes as part of risk assessment and treatment activities? | N/A | Risk reviews of changes will begin once the system architecture stabilises in beta. | N/A
Action 60 | Are you appropriately escalating any changes that create risks above the project's risk appetite? | N/A | No changes requiring risk escalation have occurred at this phase. | N/A
Retiring service components securely will help you meet principles 7 and 10 |  |  |  | 0
Action 61 | Have you identified components to be retired in the asset inventory? | Yes | Legacy components identified for retirement are logged in the asset register. Evidence: Asset_Register_009.1.xlsx. | 1
Action 62 | Have you conducted a retirement risk assessment with an appropriate plan put together based on the classification and sensitivity of data? | Yes | Retirement risk assessment has been completed based on data sensitivity. Evidence: Component_Retirement_Assessment_Alpha.docx. | 1
Action 63 | Have you included security considerations within a formal closeout report to be shared with relevant stakeholders? | Yes | Security considerations have been captured in the Alpha phase closeout report. Evidence: Alpha_Closeout_Report_Security_Section.pdf. | 1
End of worksheet |  |  |  | 5.6604
81.8449
Note on B2: The tracker starts at a 'Low' confidence status by default. The confidence status increases to 'Medium' or 'High' based on the responses you provide.
Note on B5: It is important to identify the stakeholders with an interest in the service and give them the opportunity to provide input into security elements of the business case so it reflects their needs.
Note on B6: Cyber security should be considered from the start of a project and included in the business case so sufficient resources can be secured for responding to and mitigating risks.
Note on B7: This will help support the case for necessary cyber security investment.
Note on B8: Providing the pros and cons of security approaches will help demonstrate the need for investment in security.
Note on B9: This should include the relevant governance and assurance frameworks and outline the rules and responsibilities of senior stakeholders.
Note on B11: An agreed plan with the required security skills will ensure that the security related tasks will be executed by the Suitable Qualified and Experienced Person team.
Note on B12: This will help security resources be appropriately allocated throughout the delivery life cycle.
Note on B13: This will help establish what security tools will be required across the life cycle of the service.
Note on B14: This will allow the design of the service to conform to the baseline security controls embedded in established patterns, reducing the resources required to carry out cyber security activities.
Note on B16: This will provide clarity on each individual's role, identify any gaps, and increase the likelihood that security activities will have appropriate governance and oversight. Refer to the indicative Secure by Design RACI Matrix.
Note on B17: This means delivery risk decisions will be made by a senior stakeholder, helping to reduce roadblocks where approval is required.
Note on B19: This will ensure a lightweight process to maintain a measure of confidence as to whether the project team is following the Secure by Design approach.
Note on B21: This allows identified security risks to be articulated, evaluated and escalated in relation to the organisation’s risk tolerance.
Note on B22: This increases the likelihood that the right protocols are followed for risks that need to be prioritised or escalated, enabling early action to be taken on priority risks.
Note on B23: This ensures the security posture of other organisations is factored in when managing security risks.
Note on B24: This will inform the security controls that you need to implement in order to meet the NCSC CAF outcomes and Indicators of Good Practice (IGP). Read more at https://www.security.gov.uk/guidance/govassure
Note on B25: This will inform the security controls that you need to implement in order to meet the NCSC CAF outcomes and Indicators of Good Practice (IGP). Read more at https://www.security.gov.uk/guidance/govassure
Note on B27: This will help identify any risks related to data sharing, access and management by third-party vendors.
Note on B28: This will highlight any security risks related to data sharing and access that need to be managed before accepting MSP contracts.
Note on B29: Security due diligence of third party technology products and vendors allows you to identify and assess any associated risks.
Note on B30: This allows you to clearly communicate identified risks to stakeholders and collaborate on mitigating or responding to them.
Note on B32: This allows delivery teams to have an accurate picture of assets so they can support asset owners to qualify the impact to the organisation should the assets be compromised.
Note on B33: Establishing responsibility for service assets increases the likelihood they will be effectively described and understood.
Note on B35: Assessing the business impact should the confidentiality and integrity of data assets and availability of the service be compromised supports the project team in understanding the importance of the assets and in evaluating the security risks further down the line during the risk assessment activities.
Note on B36: The business stakeholders are better placed to assess the impact of a security breach of an asset. Engaging with them enables the delivery and security teams to implement security controls that are commensurate to the business impact of a breach.
Note on B38: This will give you an understanding of the threats faced by the organisation so you can assess the associated risks to your service.
Note on B39: This is essential for identifying and prioritising threats effectively so you can demonstrate that proposed risk mitigation strategies have sufficiently considered the severity of threats.
Note on B40: This is crucial for identifying emerging threats and understanding attack patterns for threat actors so risk mitigation strategies can be adjusted accordingly.
Note on B42: This will allow delivery and security teams to have a better understanding of the service to use in threat modelling activities.
Note on B43: This should be repeated a number of times throughout service delivery as the threat landscape and attack surface change.
Note on B44: This allows you to demonstrate security controls have been effectively assessed so cost efficient mitigation strategies can be put in place to meet evolving security threats.
Note on B45: Implementing a single control that addresses multiple threats can lead to significant cost savings and help to prioritise security resources.
Note on B46: A security design review helps make sure the system follows best practices, reduces risks, and meets security standards.
Note on B48: This allows for consistency across your organisation so security risks follow the same prioritisation approach as other types of risk (such as financial, operational and so on).
Note on B49: This allows future risk assessments to be carried out using repeatable methods which is important for consistency, risk coverage, decision making, compliance, and efficiency.
Note on B50: This ensures delivery teams are using the most current and relevant information to make informed decisions on risk mitigation measures, reducing the risk of damage to the service and organisation.
Note on B51: Regularly reviewing and updating your risk register ensures the risk management plan remains effective and any new risks are identified and addressed promptly.
Note on B53: This will help delivery teams to select appropriate security controls from recognised industry frameworks as part of risk mitigation activities.
Note on B54: Engaging with security teams within your organisation will ensure the security controls you identify are compatible with the approach they are taking.
Note on B55: This will be used by those developing an approach for responding to and mitigating security risks.
Note on B56: This will help demonstrate your compliance with the NCSC CAF and help you achieve your GovAssure profile.
Note on B58: Any remaining risks without mitigations in place should be considered acceptable by the Senior Responsible Owner (SRO) and service owner.
Note on B59: This must be maintained as part of ongoing risk management activities throughout the service delivery life cycle.
Note on B61: The security controls you implement should be proportionate to the risks in order to justify the security investment.
Note on B62: This provides a comprehensive record of the measures taken to reduce risk which can be used by delivery teams, and by compliance teams when demonstarting regulatory requirements have been met.
Note on B63: This will help ensure they are effective in protecting your service and identify any potential weaknesses.
Note on B64: Any risks that are not mitigated by security controls should be deemed acceptable by your Senior Responsible Owner (SRO) or service owner, or both.
Note on B66: This allows you to focus efforts on the vulnerabilities that are most critical to your service and reduce the chance of them being exploited by attackers.
Note on B67: This will help you to quickly mitigate the risk of an attack from vulnerabilities that are currently unknown to you or third-party vendors.
Note on B69: This will minimise project risks by providing a high level of control during development processes, reducing the cost and impact of software flaws and vulnerabilities.
Note on B70: Review processes help you improve code quality and security, while improving collaboration and learning across your team.
Note on B71: This will reduce security risks by providing immediate feedback on issues introduced into code during development.
Note on B72: These should take place throughout the service delivery life cycle to provide regular security assurance.
Note on B74: This will allow you to develop a risk-based approach that considers compliance and incident response requirements.
Note on B75: This will ensure your security operations team are able to effectively respond to system-related issues or potential security incidents.
Note on B76: It is essential to develop an approach for logging analysis and monitoring for alerting the security operations team to system-related issues or potential security incidents.
Note on B78: This is essential for maintaining a secure environment and continuous compliance with relevant regulations.
Note on B79: Revisiting the threat model will allow you to assess the potential impact of the service when major changes are made.
Note on B80: Whenever there is a major change, it is important to revisit the security risk assessment to identify new risks that might be introduced as a result of the change.
Note on B81: Risk owners should be kept informed of any potential changes that affect the service’s risk profile.
Note on B83: This will ensure you have the necessary information to determine the security impact of retiring the components on the service and organisation.
Note on B84: This will allow the appropriate security responses or mitigations to be put in place when carrying out the retirement.
Note on B85: Your service owner, SRO, data owners, Chief Information Security Office (CISO) and Chief Digital Information Officer (CDIO) may need to be made aware of the security implications of the full or partial retirement of service components.

## Private beta
Private beta phase worksheet. This table contains actions 1 to 54. The table begins in cell A2. Rows 1, 2 and 3 are frozen. The table direction is left to right.
Confidence status: | High | Congratulations! This project has achieved the required confidence score.
Reference | Questions | Response | Notes or evidence | Response score
Considering security within the business case will help you meet principles 1, 2, 3, 4 and 9
Action 1 | Have you consulted relevant security stakeholders when developing your business case? | Yes | The team actively engaged key security stakeholders during the update the Full Business Case for gate 4. Discussions and decisions are documented in Security_Stakeholder_Engagement_Log_PrivateBeta_v1.1.docx. | 1
Action 2 | Does the business case include cyber security considerations? | Yes | We incorporated cyber security considerations into the Full Business Case, as detailed in Full_Business_Case_Gate4_FINAL.pdf. | 1
Action 3 | Does the economic case include an analysis with the security threats, security risk tolerance, security objectives and cyber resilience as part of critical success factors? | No | The economic case currently lacks an analysis of security threats, risk tolerance, objectives and resilience. This gap is noted in Economic_Case_Draft_v0.9.docx and requires resolution in the next iteration. | 0
Action 4 | Does the economic case consider varying levels of security when calculating value for money? | Yes | We considered varying levels of security when evaluating value for money. The analysis is presented in Economic_Case_Security_Assumptions_Analysis.xlsx. | 1
Action 5 | Does the management case include details of the security governance and assurance approach? | Yes | The management case outlines our approach to security governance and assurance, which is fully described in Management_Case_Security_Governance_v1.0.docx. | 1
Identifying security resources will help you meet principle 1 |  |  |  | 5.1799
Action 6 | Does the project have a resource plan showing security roles and skills required to support the delivery of the service? | Yes | We developed a detailed resource plan that specifies required security roles and capabilities. This can be reviewed in Security_Resource_Plan_PrivateBeta.xlsx. | 1
Action 7 | Have you identified and captured the skills required to carry out security activities and engaged with your organisation's security team to support the delivery? | Yes | Our team identified the required security skills and engaged our internal security team to support delivery. Details are captured in Security_Skills_Inventory_and_Engagement_Notes.pdf. | 1
Action 8 | Have you identified and captured the required technology resources such as software development environments, tools and security capabilities that will be required for the project? | Yes | We documented all necessary technology resources, including tools and security components, in Security_Technology_Requirements_PrivateBeta_v1.3.xlsx. | 1
Action 9 | Have you considered pre-approved or recommended architectural patterns available from your organisation or other government departments? | Yes | We reviewed and adopted pre-approved architectural patterns provided by internal architecture teams and the wider government community. Evidence is in Security_Architecture_Guidance_Review_v2.0.pdf. | 1
Agreeing roles and responsibilities will help you meet principle 1 |  |  |  | 3.5971
Action 10 | Have you assigned the Secure by Design responsibilities (for example, in a RACI matrix) and communicated them to the relevant parties? | Yes | We assigned Secure by Design responsibilities using a RACI matrix and communicated them to all relevant stakeholders. See SecureByDesign_RACI_Matrix_PrivateBeta_v1.1.xlsx. | 1
Action 11 | Have you appointed a Senior Responsible Owner (SRO), service owner or equivalent, and informed the individual of their responsibilities? | Yes | We formally appointed a service owner and communicated their responsibilities. See SRO_ServiceOwner_Appointment_Letters.pdf. | 1
Tracking Secure by Design progress will help you meet principle 9 |  |  |  | 5.7554
Action 12 | Have you included continuous assurance processes in the service's project delivery workflow? | Yes | We have considered all Secure by Design activities for discovery as recommended in the How to integrate Secure by Design into the government gate review life cycle guidance. We've added these to the backlog and created epics for each, which span a number of sprints. | 1
Managing third-party product security risks will help you meet principle 2 |  |  |  | 7.1942
Action 13 | Have you reviewed the security risks of any cloud technology (such as IaaS, PaaS, SaaS) before using it? | Yes | We completed a comprehensive review of cloud security risks using the NCSC cloud security principles before committing to infrastructure choices. Details are outlined in Cloud_Technology_Security_Assessment_PrivateBeta_v1.0.docx. | 1
Action 14 | Have you identified the security risks related to third-party Managed Service Providers (MSPs) before using them? | N/A | This activity is not applicable, as no MSPs are involved in the current delivery phase. | N/A
Action 15 | Have you assessed and managed the risks associated with any third-party development environments or software before committing to using them? | Yes | We assessed third-party software and development environment risks during alpha. Documentation is available in ThirdParty_Security_Risk_Assessment_Alpha_v0.8.docx. | 1
Action 16 | Have you created a report that highlights any security risks associated with using third-party products, including recommendations on how to manage those risks? | Yes | We compiled a formal report on third-party product risks, including recommended mitigations. See ThirdParty_Security_Risk_Report_PrivateBeta_FINAL.pdf. | 1
Documenting service assets will help you meet principles 3 and 7 |  |  |  | 4.3165
Action 17 | Have you identified and documented the business and technology information assets in scope of the service? | Yes | We identified and catalogued all business and technology assets in scope in Service_Asset_Inventory_PrivateBeta_v1.2.xlsx. | 1
Action 18 | Have you identified and documented a service owner or information asset owner for each asset? | Yes | We assigned owners for each identified asset and documented these in Asset_Ownership_Assignment_Register_v1.0.docx. | 1
Assessing the importance of service assets will help you meet principle 3 |  |  |  | 5.036
Action 19 | Have you completed a business impact assessment to determine the confidentiality, integrity and availability of data if the service was compromised? | Yes | The team completed a full Business Impact Assessment to evaluate potential consequences of service compromise. See Business_Impact_Assessment_PrivateBeta_v1.0.pdf. | 1
Action 20 | Did you consult with business stakeholders when creating the impact assessment? | Yes | We consulted business stakeholders during the impact assessment and documented their inputs in BIA_Stakeholder_Workshop_Minutes.pdf. | 1
Performing threat modelling will help you meet principles 3 and 7 |  |  |  | 5.036
Action 21 | Have you documented the technical architecture for the end-to-end service and system? | Yes | We documented the full technical architecture of the service in EndToEnd_Service_Architecture_PrivateBeta_v1.2.pdf. | 1
Action 22 | Have you identified and documented the possible attack paths or threat events that could be used to exploit vulnerabilities in the service? | Yes | We conducted threat modelling to identify possible attack vectors, recorded in Threat_Modelling_Documentation_v1.0.drawio.pdf. | 1
Action 23 | Have you identified and documented what security controls are available to reduce the likelihood of threat events? | Yes | We identified relevant security controls to address known threats and documented these in Security_Controls_Catalogue_v1.1.xlsx. | 1
Action 24 | Have you identified and documented any security controls that could mitigate multiple threat events? | Yes | We highlighted controls capable of mitigating multiple threat scenarios. This is outlined in Security_Control_Mapping_Table_v1.0.xlsx. | 1
Action 25 | Have you conducted a security design review against good practice principles and patterns? | Yes | We conducted a security design review of our SaaS-based solution against NCSC’s Cloud Security Principles, OWASP SaaS Checklist and ISO/IEC 27017 cloud-specific controls. The review ensured that authentication, access control, data security and multitenancy risks were adequately addressed. The completed checklist and supporting materials are documented in Security_Design_Review_SaaS_PrivateBeta_v1.0.pdf. | 1
Performing a security risk assessment will help you meet principle 3 |  |  |  | 5.7554
Action 26 | Do the scoring scales used for your service's security risk assessment align with your organisation's risk management processes? | Yes | The risk scoring scales have been obtained from risk and complance and are aligned with corporate risk management policies. The model used is in Risk_Assessment_Scoring_Model_v2.0.docx. | 1
Action 27 | Have you documented the risk assessment method used to perform a risk assessment? | Yes | We use a methodology consistent with ISO27005 which is documented in Security_Risk_Assessment_Methodology_v1.0.pdf. | 1
Action 28 | Have you validated the timeliness of the threat and business impact sources? | Yes | We validated the relevance and accuracy of threat intelligence and business impact sources with input from our assurance team. The threat assessment is dated Jan 2025 and business impact reference table was refreshed in Dec 2024. | 1
Action 29 | Have you documented the service's risks (for example in a risk register)? | Yes | We maintain an up-to-date risk register for the service, which is available in PrivateBeta_Risk_Register_v1.2.xlsx. | 1
Agreeing a security controls set for your service will help you meet principles 3 and 10 |  |  |  | 7.1942
Action 30 | Have you identified the cyber security standards that are relevant to the service? | Yes | We identified all applicable cyber security standards for this service: NIST Cybersecurity Framework and CSA Security, Trust & Assurance Registry. | 1
Action 31 | Have you agreed the security control frameworks you intend to use with your organisation’s security function? | Yes | We agreed on the security control frameworks with the security function and recorded this in Security_Framework_Agreement_Notes_v1.0.pdf. | 1
Action 32 | Have you created a security controls set relevant to your service? | Yes | We created a bespoke security control set, aligned to the service needs. Refer to Service_Specific_Security_Controls_Set_v1.0.xlsx. | 1
Action 33 | Does your security controls set map to the NCSC Cyber Assessment Framework (CAF)? | No |  | 0
Responding to and mitigating security risks will help you meet principles 3, 4, 5, 6, 7 and 8 |  |  |  | 4.8561
Action 34 | Have you treated the risks that have a rating above the project's risk appetite? | Yes | We addressed all risks exceeding our appetite and documented treatment actions in Risk_Treatment_Log_PrivateBeta_v1.1.xlsx. | 1
Action 35 | Have you documented the risk mitigations (for example in a risk treatment plan)? | Yes | We produced a risk treatment plan detailing how high-priority risks will be managed. See Risk_Treatment_Plan_v1.0.docx. | 1
Assessing the effectiveness of security controls will help you meet principles 4, 5, 6, 7 and 8 |  |  |  | 7.1942
Action 36 | Did you select the security controls based on risk, threats and exposure? | Yes | Our control selection was based on identified threats, risks, and potential exposure, outlined in Security_Control_Selection_Rationale_v1.0.pdf. | 1
Action 37 | Have you documented the selected controls? | Yes | We documented the chosen controls in a central register. See Selected_Security_Controls_Repository.xlsx. | 1
Action 38 | Have you tested the controls and confirmed they're working as intended? | Yes | We tested all implemented controls and confirmed their effectiveness, recorded in Security_Control_Test_Results_PrivateBeta_v1.0.docx. | 1
Action 39 | Have you identified any residual risks and raised them with risk owners for sign-off? | Yes | Residual risks were escalated and formally signed off by the service owners. Evidence is in Residual_Risk_SignOff_Log_v1.0.xlsx. | 1
Implementing a vulnerability management process will help you meet principles 5 and 9 |  |  |  | 7.1942
Action 40 | Do you have a documented approach on how to classify, prioritise and redress vulnerabilities? | Yes | We established a clear policy for classifying and prioritising vulnerabilities, outlined in Vulnerability_Management_Strategy_v1.0.pdf. | 1
Action 41 | Do you have a documented process for identifying and responding to new vulnerabilities in your code, systems or supply chain? | Yes | We documented our approach to detecting and responding to new vulnerabilities in Security_Vulnerability_Response_Process_v1.1.docx. | 1
Discovering vulnerabilities will help you meet principles 2, 5 and 7 |  |  |  | 5.7554
Action 42 | Are you following a secure systems software development life cycle policy or process? | Yes | We followed our secure software development lifecycle, as outlined in Secure_Software_Development_Lifecycle_Policy_v1.0.pdf. | 1
Action 43 | Are you conducting regular code reviews as part of the development process? | Yes | We performed regular peer code reviews, with logs maintained in Code_Review_Log_Jan_to_May_2025.xlsx. | 1
Action 44 | Are you using a manual or automated code testing method (for example, Static Application Security Testing (SAST) or Dynamic Application Security Testing (DAST))? | Yes | We used both SAST and DAST tools to test our code. Results are summarised in Code_Testing_Reports_Q1_2025_SAST_DAST.pdf. | 1
Action 45 | Do you have a plan for carrying out penetration tests with appropriate scopes? | Yes | We developed a penetration test plan with clearly defined scope and schedule. See Penetration_Test_Plan_PrivateBeta_v1.0.pdf. | 1
Managing observability will help you meet principles 5 and 7 |  |  |  | 5.7554
Action 46 | Do you have a documented approach for what events should be logged to help identify security incidents? | Yes | We created a logging policy that defines which security events should be captured. See Security_Event_Logging_Guidance_v1.0.docx. | 1
Action 47 | Have you determined the tools required to log and analyse the event logs and trigger alerts? | Yes | We identified and procured the required logging and alerting tools, detailed in Log_Analysis_Tools_Selection_Document_v1.0.xlsx. | 1
Action 48 | Do you have a documented approach for analysing your logs and monitoring the alerts generated? | Yes | We outlined our process for monitoring logs and acting on alerts in Log_Monitoring_SOP_v1.1.docx. | 1
Evaluating the security impact of changes will help you meet principle 10 |  |  |  | 5.7554
Action 49 | Does the service delivery change management process consider the impact of changes to security? | N/A | Not applicable. No service changes have occurred that impact security during private beta. | N/A
Action 50 | Are you reflecting requested changes in the service’s threat model? | N/A | Not applicable. The threat model has not changed due to lack of major updates. | N/A
Action 51 | Are you considering requested changes as part of risk assessment and treatment activities? | N/A | Not applicable. There have been no change-related risk assessments to date. | N/A
Action 52 | Are you appropriately escalating any changes that create risks above the project's risk appetite? | N/A | Not applicable. No escalations were necessary as risk levels remained within tolerance. | N/A
Retiring service components securely will help you meet principles 7 and 10 |  |  |  | 0
Action 53 | Have you identified components to be retired in the asset inventory? | N/A | Not applicable. No service components are being retired during this delivery phase. | N/A
Action 54 | Have you conducted a retirement risk assessment with an appropriate plan put together based on the classification and sensitivity of data? | N/A | Not applicable. Retirement planning is not yet in scope. | N/A
Action 55 | Have you included security considerations within a formal closeout report to be shared with relevant stakeholders? | N/A | Not applicable. No formal service closeout has taken place at this stage. | N/A
End of worksheet |  |  |  | 0
85.5755
Note on B2: The tracker starts at a 'Low' confidence status by default. The confidence status increases to 'Medium' or 'High' based on the responses you provide.
Note on B5: It is important to identify the stakeholders with an interest in the service and give them the opportunity to provide input into security elements of the business case so it reflects their needs.
Note on B6: Cyber security should be considered from the start of a project and included in the business case so sufficient resources can be secured for responding to and mitigating risks.
Note on B7: This will help support the case for necessary cyber security investment.
Note on B8: Providing the pros and cons of security approaches will help demonstrate the need for investment in security.
Note on B9: This should include the relevant governance and assurance frameworks and outline the rules and responsibilities of senior stakeholders.
Note on B11: An agreed plan with the required security skills will ensure that the security related tasks will be executed by the Suitable Qualified and Experienced Person team.
Note on B12: This will help security resources be appropriately allocated throughout the delivery life cycle.
Note on B13: This will help establish what security tools will be required across the life cycle of the service.
Note on B14: This will allow the design of the service to conform to the baseline security controls embedded in established patterns, reducing the resources required to carry out cyber security activities.
Note on B16: This will provide clarity on each individual's role, identify any gaps, and increase the likelihood that security activities will have appropriate governance and oversight. Refer to the indicative Secure by Design RACI matrix.
Note on B17: This means delivery risk decisions will be made by a senior stakeholder, helping to reduce roadblocks where approval is required.
Note on B19: This will ensure a lightweight process to maintain a measure of confidence as to whether the project team is following the Secure by Design approach.
Note on B21: This will help identify any risks related to data sharing, access and management by third-party vendors.
Note on B22: This will highlight any security risks related to data sharing and access that need to be managed before accepting MSP contracts.
Note on B23: Security due diligence of third-party technology products and vendors allows you to identify and assess any associated risks.
Note on B24: This allows you to clearly communicate identified risks to stakeholders and collaborate on mitigating or responding to them.
Note on B26: This allows delivery teams to have an accurate picture of assets so they can support asset owners to qualify the impact to the organisation should the assets be compromised.
Note on B27: Establishing responsibility for service assets increases the likelihood they will be effectively described and understood.
Note on B29: Assessing the business impact should the confidentiality and integrity of data assets and availability of the service be compromised supports the project team in understanding the importance of the assets and in evaluating the security risks further down the line during the risk assessment activities.
Note on B30: The business stakeholders are better placed to assess the impact of a security breach of an asset. Engaging with them enables the delivery and security teams to implement security controls that are commensurate to the business impact of a breach.
Note on B32: This will allow delivery and security teams to have a better understanding of the service to use in threat modelling activities.
Note on B33: This should be repeated a number of times throughout service delivery as the threat landscape and attack surface change.
Note on B34: This allows you to demonstrate security controls have been effectively assessed so cost efficient mitigation strategies can be put in place to meet evolving security threats.
Note on B35: Implementing a single control that addresses multiple threats can lead to significant cost savings and help to prioritise security resources.
Note on B36: A security design review helps make sure the system follows best practices, reduces risks, and meets security standards.
Note on B38: This allows for consistency across your organisation so security risks follow the same prioritisation approach as other types of risk (such as financial, operational and so on).
Note on B39: This allows future risk assessments to be carried out using repeatable methods which is important for consistency, risk coverage, decision making, compliance, and efficiency.
Note on B40: This ensures delivery teams are using the most current and relevant information to make informed decisions on risk mitigation measures, reducing the risk of damage to the service and organisation.
Note on B41: Regularly reviewing and updating your risk register ensures the risk management plan remains effective and any new risks are identified and addressed promptly.
Note on B43: This will help delivery teams to select appropriate security controls from recognised industry frameworks as part of risk mitigation activities.
Note on B44: Engaging with security teams within your organisation will ensure the security controls you identify are compatible with the approach they are taking.
Note on B45: This will be used by those developing an approach for responding to and mitigating security risks.
Note on B46: This will help demonstrate your compliance with the NCSC CAF and help you achieve your GovAssure profile.
Note on B48: Any remaining risks without mitigations in place should be considered acceptable by the Senior Responsible Owner (SRO) and service owner.
Note on B49: This must be maintained as part of ongoing risk management activities throughout the service delivery lifecycle.
Note on B51: The security controls you implement should be proportionate to the risks in order to justify the security investment.
Note on B52: This provides a comprehensive record of the measures taken to reduce risk which can be used by delivery teams, and by compliance teams when demonstarting regulatory requirements have been met.
Note on B53: This will help ensure they are effective in protecting your service and identify any potential weaknesses.
Note on B54: Any risks that are not mitigated by security controls should be deemed acceptable by your SRO or service owner, or both.
Note on B56: This allows you to focus efforts on the vulnerabilities that are most critical to your service and reduce the chance of them being exploited by attackers.
Note on B57: This will help you to quickly mitigate the risk of an attack from vulnerabilities that are currently unknown to you or third-party vendors.
Note on B59: This will minimise project risks by providing a high level of control during development processes, reducing the cost and impact of software flaws and vulnerabilities.
Note on B60: Review processes help you improve code quality and security, while improving collaboration and learning across your team.
Note on B61: This will reduce security risks by providing immediate feedback on issues introduced into code during development.
Note on B62: These should take place throughout the service delivery life cycle to provide regular security assurance.
Note on B64: This will allow you to develop a risk-based approach that considers compliance and incident response requirements.
Note on B65: This will ensure your security operations team are able to effectively respond to system-related issues or potential security incidents.
Note on B66: It is essential to develop an approach for logging analysis and monitoring for alerting the security operations team to system-related issues or potential security incidents.
Note on B68: This is essential for maintaining a secure environment and continuous compliance with relevant regulations.
Note on B69: Revisiting the threat model will allow you to assess the potential impact of the service when major changes are made.
Note on B70: Whenever there is a major change, it is important to revisit the security risk assessment to identify new risks that might be introduced as a result of the change.
Note on B71: Risk owners should be kept informed of any potential changes that affect the service’s risk profile.
Note on B73: This will ensure you have the necessary information to determine the security impact of retiring the components on the service and organisation.
Note on B74: This will allow the appropriate security responses or mitigations to be put in place when carrying out the retirement.
Note on B75: Your service owner, SRO, data owners, Chief Information Security Office (CISO) and Chief Digital Information Officer (CDIO) may need to be made aware of the security implications of the full or partial retirement of service components.

## Public beta or live
Public beta or live phase worksheet. This table contains actions 1 to 23. The table begins in cell A2. Rows 1, 2 and 3 are frozen. The table direction is left to right.
Confidence status: | Low | This project has not achieved the required confidence score and will not get spend control approval.
Reference | Questions | Response | Notes or evidence | Response score
Considering security within the business case will help you meet principles 1, 2, 3, 4 and 9
Action 1 | Have you consulted relevant security stakeholders when developing your business case? | Select answer... |  | 0
Action 2 | Does the business case include cyber security considerations? | Select answer... |  | 0
Action 3 | Does the economic case include an analysis with the security threats, security risk tolerance, security objectives and cyber resilience as part of critical success factors? | Select answer... |  | 0
Action 4 | Does the economic case consider varying levels of security when calculating value for money? | Select answer... |  | 0
Action 5 | Does the management case include details of the security governance and assurance approach? | Select answer... |  | 0
Tracking Secure by Design progress will help you meet principle 9 |  |  |  | 0
Action 6 | Have you included continuous assurance processes in the service's project delivery workflow? | Select answer... |  | 0
Responding to and mitigating security risks will help you meet principles 3, 4, 5, 6, 7 and 8 |  |  |  | 0
Action 7 | Have you treated the risks that have a rating above the project's risk appetite? | Select answer... |  | 0
Action 8 | Have you documented the risk mitigations (for example in a risk treatment plan)? | Select answer... |  | 0
Assessing the effectiveness of security controls will help you meet principles 4, 5, 6, 7 and 8 |  |  |  | 0
Action 9 | Did you select the security controls based on risk, threats and exposure? | Select answer... |  | 0
Action 10 | Have you documented the selected controls? | Select answer... |  | 0
Action 11 | Have you tested the controls and confirmed they're working as intended? | Select answer... |  | 0
Action 12 | Have you identified any residual risks and raised them with risk owners for sign-off? | Select answer... |  | 0
Discovering vulnerabilities will help you meet principles 2, 5 and 7 |  |  |  | 0
Action 13 | Are you following a secure systems software development life cycle policy or process? | Select answer... |  | 0
Action 14 | Are you conducting regular code reviews as part of the development process? | Select answer... |  | 0
Action 15 | Are you using a manual or automated code testing method (for example, Static Application Security Testing (SAST) or Dynamic Application Security Testing (DAST))? | Select answer... |  | 0
Action 16 | Do you have a plan for carrying out penetration tests with appropriate scopes? | Select answer... |  | 0
Evaluating the security impact of changes will help you meet principle 10 |  |  |  | 0
Action 17 | Does the service delivery change management process consider the impact of changes to security? | Select answer... |  | 0
Action 18 | Are you reflecting requested changes in the service’s threat model? | Select answer... |  | 0
Action 19 | Are you considering requested changes as part of risk assessment and treatment activities? | Select answer... |  | 0
Action 20 | Are you appropriately escalating any changes that create risks above the project's risk appetite? | Select answer... |  | 0
Retiring service components securely will help you meet principle 7 and 10 |  |  |  | 0
Action 21 | Have you identified components to be retired in the asset inventory? | Select answer... |  | 0
Action 22 | Have you conducted a retirement risk assessment with an appropriate plan put together based on the classification and sensitivity of data? | Select answer... |  | 0
Action 23 | Have you included security considerations within a formal closeout report to be shared with relevant stakeholders? | Select answer... |  | 0
End of worksheet |  |  |  | 0
0
Note on B2: The tracker starts at a 'Low' confidence status by default. The confidence status increases to 'Medium' or 'High' based on the responses you provide.
Note on B5: It is important to identify the stakeholders with an interest in the service and give them the opportunity to provide input into security elements of the business case so it reflects their needs.
Note on B6: Cyber security should be considered from the start of a project and included in the business case so sufficient resources can be secured for responding to and mitigating risks.
Note on B7: This will help support the case for necessary cyber security investment.
Note on B8: Providing the pros and cons of security approaches will help demonstrate the need for investment in security.
Note on B9: This should include the relevant governance and assurance frameworks and outline the rules and responsibilities of senior stakeholders.
Note on B11: This will ensure a lightweight process to maintain a measure of confidence as to whether the project team is following the Secure by Design approach.
Note on B13: Any remaining risks without mitigations in place should be considered acceptable by the Senior Responsible Owner (SRO) and service owner.
Note on B14: This must be maintained as part of ongoing risk management activities throughout the service delivery life cycle.
Note on B16: The security controls you implement should be proportionate to the risks in order to justify the security investment.
Note on B17: This provides a comprehensive record of the measures taken to reduce risk which can be used by delivery teams, and by compliance teams when demonstarting regulatory requirements have been met.
Note on B18: This will help ensure they are effective in protecting your service and identify any potential weaknesses.
Note on B19: Any risks that are not mitigated by security controls should be deemed acceptable by your SRO or service owner, or both.
Note on B21: This will minimise project risks by providing a high level of control during development processes, reducing the cost and impact of software flaws and vulnerabilities.
Note on B22: Review processes help you improve code quality and security, while improving collaboration and learning across your team.
Note on B23: This will reduce security risks by providing immediate feedback on issues introduced into code during development.
Note on B24: These should take place throughout the service delivery life cycle to provide regular security assurance.
Note on B26: This is essential for maintaining a secure environment and continuous compliance with relevant regulations.
Note on B27: Revisiting the threat model will allow you to assess the potential impact of the service when major changes are made.
Note on B28: Whenever there is a major change, it is important to revisit the security risk assessment to identify new risks that might be introduced as a result of the change.
Note on B29: Risk owners should be kept informed of any potential changes that affect the service’s risk profile.
Note on B31: This will ensure you have the necessary information to determine the security impact of retiring the components on the service and organisation.
Note on B32: This will allow the appropriate security responses or mitigations to be put in place when carrying out the retirement.
Note on B33: Your service owner, SRO, data owners, Chief Information Security Office (CISO) and Chief Digital Information Officer (CDIO) may need to be made aware of the security implications of the full or partial retirement of service components.

## Release notes
Release notes worksheet. This table contains release date, version number and changes. The table begins in cell A2. The table direction is left to right.
Release date | Version number | Changes
Wednesday 7 May 2025 | Beta v1.1 | • In the Excel version of the Project profile worksheet, the Delivery phase dropdown was showing 7 options instead of 4. This was because Excel uses commas to separate options. We've changed this to hyphens, so 'Alpha or Design, build' is now 'Alpha or Design-build' and 'Private beta or Design, build, test, implement' is now 'Private beta or Design-build-test-implement'. • For clarity, rephrased action relating to continuous assurance processes (action 12 on Discovery, Alpha and Private beta worksheets and action 6 on Public beta or live worksheet) • For clarity, rephrased action relating to automated code testing methods (action 52 on Alpha worksheet, action 44 on Private beta worksheet and action 15 on Public beta or live) • Created release notes worksheet
Wednesday 2 April 2025 | Beta v1.0 | • New impact-driven approach to weighting • Separate worksheets for each delivery phase, with relevant actions for each • Addition of dashboard showing confidence statuses for each delivery phase • Notes added detailing why each action is important • More detailed project profile summary • Addition of document control table • Statements changed to questions • Accessibility improvements, including increased font size, index worksheet for navigation, worksheet descriptions, accessible colour contrast, left-aligned text content, unmerged cells and so on • Protected worksheets to avoid changes to formulae
Friday 22 November 2024 | Alpha v2.0
Friday 16 February 2024 | Alpha v1.0

## Weighting (hidden)
Weighting worksheet. This table contains 21 activities, categorised into 5 themes. There are weightings between 0 (low) and 10 (high) for each of the 4 phases (discovery, alpha, private beta and public beta or live). The table begins in cell A2. Columns D, F and H are hidden. The table direction is left to right.
Activity group | Activity guidance | Discovery phase activities | Discovery Phase Activities in % | Alpha activities | Alpha Activities in % | Private beta activities | Private Beta Activities in % | Public beta or live activities | Public Beta or Live Activities in % | Public Beta or Live Activities in %
Prepare a secure service | Considering security within the business case | 9 | 9.5745 | 9 | 5.6604 | 9 | 6.4748 | 4 | 7.4074 | 7.4074
Prepare a secure service | Identifying security resources | 7 | 7.4468 | 7 | 4.4025 | 5 | 3.5971 | 0 | 0 | 0
Prepare a secure service | Agreeing roles and responsibilities | 8 | 8.5106 | 8 | 5.0314 | 8 | 5.7554 | 0 | 0 | 0
Prepare a secure service | Tracking Secure by Design progress | 10 | 10.6383 | 10 | 6.2893 | 10 | 7.1942 | 10 | 18.5185 | 18.5185
Prepare a secure service | Working out the project’s security risk appetite | 9 | 9.5745 | 9 | 5.6604 | 0 | 0 | 0 | 0 | 0
Understand the security landscape | Managing third-party product security risks | 6 | 6.383 | 7 | 4.4025 | 6 | 4.3165 | 0 | 0 | 0
Understand the security landscape | Understanding cyber security obligations | 8 | 8.5106 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Understand the security landscape | Understanding business objectives and user needs | 9 | 9.5745 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manage cyber security risks | Documenting service assets | 9 | 9.5745 | 8 | 5.0314 | 7 | 5.036 | 0 | 0 | 0
Manage cyber security risks | Assessing the importance of service assets | 9 | 9.5745 | 8 | 5.0314 | 7 | 5.036 | 0 | 0 | 0
Manage cyber security risks | Sourcing a threat assessment | 10 | 10.6383 | 9 | 5.6604 | 0 | 0 | 0 | 0 | 0
Manage cyber security risks | Performing threat modelling | 0 | 0 | 10 | 6.2893 | 8 | 5.7554 | 0 | 0 | 0
Manage cyber security risks | Performing a security risk assessment | 0 | 0 | 10 | 6.2893 | 10 | 7.1942 | 0 | 0 | 0
Manage cyber security risks | Agreeing a security controls set for your service | 0 | 0 | 9 | 5.6604 | 9 | 6.4748 | 0 | 0 | 0
Manage cyber security risks | Responding to and mitigating security risks | 0 | 0 | 10 | 6.2893 | 10 | 7.1942 | 8 | 14.8148 | 14.8148
Manage cyber security risks | Assessing the effectiveness of security controls | 0 | 0 | 5 | 3.1447 | 10 | 7.1942 | 8 | 14.8148 | 14.8148
Anticipate and respond to incidents | Implementing a vulnerability management process | 0 | 0 | 8 | 5.0314 | 8 | 5.7554 | 0 | 0 | 0
Anticipate and respond to incidents | Discovering vulnerabilities | 0 | 0 | 8 | 5.0314 | 8 | 5.7554 | 8 | 14.8148 | 14.8148
Anticipate and respond to incidents | Managing observability | 0 | 0 | 8 | 5.0314 | 8 | 5.7554 | 0 | 0 | 0
Maintain continuous assurance | Evaluating the security impact of changes | 0 | 0 | 7 | 4.4025 | 7 | 5.036 | 7 | 12.963 | 12.963
Maintain continuous assurance | Retiring service components securely | 0 | 0 | 9 | 5.6604 | 9 | 6.4748 | 9 | 16.6667 | 16.6667
|  | 94 | 100 | 159 | 100 | 139 | 100 | 54 | 100 | 100
End of worksheet
Note on C2: Criticality scale 9 to 10 = Very high 7 to 8 = High 5 to 6 = Moderate 1 to 4 = Low