## Index
Welcome to the Secure by Design example transition plan (version 2.1, February 2026). This worksheet is the index you can use to navigate to individual sheets. Index begins in cell A2. Note: Rows and columns outside of the tables are hidden to prevent accidental navigation.
Index
Principles transition plan
Activities transition plan
Adoption milestones
Release notes

## Principles transition plan
Principles transition plan worksheet This table contains Secure by Design principles and policy requirements, with cells to enter data. The table begins in cell A3. Rows 1 and 2 are frozen. The table direction is left to right.
Gaps and actions to help the organisation meet the Secure by Design principles |  | Read about the Secure by Design Principles | Read the Secure by Design Policy
Secure by Design principle | Secure by Design Policy requirement | Current assessment status | Maturity level (optional) | Identified gaps | Action ID | Proposed actions to address the gap | Status | Owner | Start date | End date | Comments Add notes on gaps and actions
1. Create responsibility for cyber security risk Assign risk owners to be accountable for managing cyber security risks for a service throughout its life cycle. These must be senior stakeholders with the experience, knowledge and authority to lead on security activities. | Have you designated an executive leadership role (such as the CDIO or equivalent) with overall accountability for the adoption of Secure by Design within the organisation? | Not started | Unknown |  |  |  | Not started
| Have you designated a senior leadership role (such as the SRO, service owner or equivalent) with overall accountability for the management of cyber security risks of digital services and technical infrastructure during their delivery? | Not started | Unknown |  |  |  | Not started
| Are there mechanisms or processes to ensure the senior leadership role has visibility of key cyber security risk decisions made throughout the digital service delivery life cycle? | Not started | Unknown |  |  |  | Not started
| Are there processes which enable regularly identifying and allocating the cyber security responsibilities required for the delivery of the digital service and technical infrastructure? | Not started | Unknown |  |  |  | Not started
| Do you have a process which ensures sufficient and suitable resources are made available to manage cyber security risks throughout the digital service life cycle, and are given the support necessary to carry out their duties? | Not started | Unknown |  |  |  | Not started
| Do you have a process for incorporating requirements for Secure by Design within commercial contracts for suppliers? | Not started | Unknown |  |  |  | Not started
2. Source secure technology products Where third-party products are used, perform security due diligence by continually assessing platforms, software and code for security vulnerabilities. Mitigate risks and share findings with suppliers to help them improve product security. | Do you have a process for carrying out security reviews on third-party products before they are implemented? | Not started | Unknown |  |  |  | Not started
| Do you have processes for mitigating any security risks associated with using third-party products to a level that meets the organisation’s and project’s security risk appetite? | Not started | Unknown |  |  |  | Not started
| Do you have processes which ensure any third-party products meet the relevant security obligations, regulations and industry security standards? | Not started | Unknown |  |  |  | Not started
| Do your processes enable making balanced decisions on the trade-off between security and usability? | Not started | Unknown |  |  |  | Not started
3. Adopt a risk-driven approach Establish the project’s risk appetite and maintain an assessment of cyber security risks to build protections appropriate to the evolving threat landscape. | Do you have a process for agreeing the security risk appetite for the digital service and sharing this across the delivery teams? | Not started | Unknown |  |  |  | Not started
| Are you documenting and prioritising the cyber security related legal, regulatory and contractual requirements that must be met by a digital service? | Not started | Unknown |  |  |  | Not started
| Do you have processes for carrying out threat modelling to understand how potential threats apply to the digital service and infrastructure as the service evolves? | Not started | Unknown |  |  |  | Not started
| Do you have processes for carrying out security risk assessments and managing identified risks during the service life cycle in line with the organisation’s approach to security risk management? | Not started | Unknown |  |  |  | Not started
| Do you have processes for communicating residual security risks to the accountable individuals and security function for incorporating these into the organisation’s risk registers? | Not started | Unknown |  |  |  | Not started
4. Design usable security controls Perform regular user research and implement findings into service design to make sure security processes are fit for purpose and easy to understand. | Do your processes take into account security-related user needs discussed in user research or captured in user stories and journeys when designing security controls? | Not started | Unknown |  |  |  | Not started
| Do your processes take into consideration business objectives included in the business case when designing security controls? | Not started | Unknown |  |  |  | Not started
5. Build in detect and respond security Design for the inevitability of security vulnerabilities and incidents. Integrate appropriate security logging, monitoring, alerting and response capabilities. These must be continually tested and iterated. | Have you implemented appropriate security logging, monitoring and alerting mechanisms to discover cyber security events and vulnerabilities? | Not started | Unknown |  |  |  | Not started
| Have you embedded effective incident response and recovery capabilities in the service design and delivery team processes? | Not started | Unknown |  |  |  | Not started
| Do you regularly test digital services and infrastructure to identify and fix weaknesses within systems before they can be exploited? | Not started | Unknown |  |  |  | Not started
6. Design flexible architectures Implement digital services and update legacy components to allow for easier integration of new security controls in response to changes in business requirements, cyber threats and vulnerabilities. | Are you using components that allow integration of new security measures in response to changes in business requirements, cyber threats and vulnerabilities? | Not started | Unknown |  |  |  | Not started
| Are you using risk-based and adaptable security architectures (for example, zero trust architectures)? | Not started | Unknown |  |  |  | Not started
| Do you test security controls and verifying they are fit for purpose before deployment? | Not started | Unknown |  |  |  | Not started
7. Minimise the attack surface Use only the capabilities, software, data and hardware components necessary for a service to mitigate cyber security risks while achieving its intended use. | Have you implemented network security measures such as network segmentation to limit the lateral movement of attackers? | Not started | Unknown |  |  |  | Not started
| Have you implemented baseline security controls, such as least privilege, anti-malware, endpoint detection and response, intrusion detection / prevention, and application allowlisting or denylisting? | Not started | Unknown |  |  |  | Not started
| Are you following secure coding practices and acting upon any relevant findings from security tests, reducing any opportunities for potential attackers to exploit vulnerabilities? | Not started | Unknown |  |  |  | Not started
| Do you have processes that enable mitigating security risks to a level that is within the acceptable risk appetite before a digital service goes live? | Not started | Unknown |  |  |  | Not started
| Do you have processes for retiring service components securely when they are no longer needed, or at the end of their life cycle? | Not started | Unknown |  |  |  | Not started
8. Defend in depth Create layered controls across a service so it’s harder for attackers to fully compromise the system if a single control fails or is overcome. | Have you created layered controls across a digital service so it’s harder for attackers to fully compromise the system if a single control fails or is overcome? | Not started | Unknown |  |  |  | Not started
| Are you implementing mechanisms to keep the impact of potential security incidents contained? | Not started | Unknown |  |  |  | Not started
| Are you testing security controls and verifying they are fit for purpose before deployment? | Not started | Unknown |  |  |  | Not started
9. Embed continuous assurance Implement continuous security assurance processes to create confidence in the effectiveness of security controls, both at the point of delivery and throughout the operational life of the service. | Are you testing security controls regularly to ensure they operate effectively and that no known vulnerabilities exist? | Not started | Unknown |  |  |  | Not started
| Do you have processes for reassessing controls against changes in the service or threat landscape? | Not started | Unknown |  |  |  | Not started
| Are you ensuring the service is built and maintained with the appropriate controls required to mitigate security risks? | Not started | Unknown |  |  |  | Not started
| Are you keeping track of adherence with Secure by Design principles throughout the digital service life cycle? | Not started | Unknown |  |  |  | Not started
| Are you providing accountable individuals and risk owners with regular evidence that security controls and capabilities are operating as intended? | Not started | Unknown |  |  |  | Not started
10. Make changes securely Embed security into the design, development and deployment processes to ensure that the security impact of changes is considered alongside other factors. | Are you assessing the security impact of changes before these are made to digital services and infrastructure? | Not started | Unknown |  |  |  | Not started
| Are you recording any residual unmitigated risks to the cyber security risk register and sharing this with the accountable individuals and security function responsible for incorporating these into the organisation’s risk registers? | Not started | Unknown |  |  |  | Not started

## Activities transition plan
Activities transition plan worksheet This table contains Secure by Design themes, questions and recommended activities, with cells to enter data. The table begins in cell A3. Rows 1 and 2 are frozen. The table direction is left to right.
Gaps and actions to help the organisation improve Secure by Design activities |  |  | View all Secure by Design activities
Secure by Design theme | Question | Secure by Design recommended activity | Assessment status | Maturity level (optional) | Identified gaps | Action ID | Proposed actions to address the gap | Status | Owner | Start date | End date | Comments Add notes on gaps and actions
Prepare a secure service | Does your organisation have processes that consider security within business cases? | Considering security within the business case | Not started | Unknown |  |  |  | Not started
| Does your organisation have processes for supporting project delivery teams to identify security resources? | Identifying security resources | Not started | Unknown |  |  |  | Not started
| Does your organisation have resources to help delivery teams understand their cyber security responsibilities as part of their agreed roles? | Agreeing roles and responsibilities | Not started | Unknown |  |  |  | Not started
| Does your organisation have a method to track the implementation of Secure by Design within projects? | Tracking Secure by Design progress | Not started | Unknown |  |  |  | Not started
| Does your organisation have a standard risk appetite statement to help delivery teams work out their project's security risk appetite? | Working out the project's security risk appetite | Not started | Unknown |  |  |  | Not started
Understand the security landscape | Does your organisation have an approach for managing third-party product security risks? | Managing third-party product security risks | Not started | Unknown |  |  |  | Not started
| Does your organisation have policies to guide projects and delivery teams understand your cyber security obligations? | Understanding cyber security obligations | Not started | Unknown |  |  |  | Not started
| Does your organisation have processes which support cyber security being part of understanding user needs? | Understanding business objectives and user needs | Not started | Unknown |  |  |  | Not started
Manage cyber security risks | Does your organisation have a approach for documenting service assets? | Documenting service assets | Not started | Unknown |  |  |  | Not started
| Does your organisation have a approach for assessing the importance of service assets? | Assessing the importance of service assets | Not started | Unknown |  |  |  | Not started
| Does your organisation have a threat assessment to support projects and delivery teams complete sourced a threat assessment? | Sourcing a threat assessment | Not started | Unknown |  |  |  | Not started
| Does your organisation have a method for performing threat modelling? | Performing threat modelling | Not started | Unknown |  |  |  | Not started
| Does your organisation have a method for performing cyber security risk assessments? | Performing a security risk assessment | Not started | Unknown |  |  |  | Not started
| Does your organisation have an agreed security controls set as part of the security assurance framework to support the build of digital services? | Agreeing a security controls set for your service | Not started | Unknown |  |  |  | Not started
| Does your organisation have a method for responding to and mitigating cyber security risks as part of the overall risk management process? | Responding to and mitigating security risks | Not started | Unknown |  |  |  | Not started
| Does your organisation have processes for assessing the effectiveness of security controls? | Assessing the effectiveness of security controls | Not started | Unknown |  |  |  | Not started
Anticipate and respond to incidents | Does your organisation have a vulnerability management process in place that new digital services can integrate with? | Implementing a vulnerability management process | Not started | Unknown |  |  |  | Not started
| Does your organisation have a process for discovering vulnerabilities? | Discovering vulnerabilities | Not started | Unknown |  |  |  | Not started
| Does your organisation have a process and suitable technology for managing observability (logging, monitoring, alerting) across projects? | Managing observability | Not started | Unknown |  |  |  | Not started
Maintain continuous assurance | Does your organisation have a process for evaluating the security impact of changes? | Evaluating the security impact of changes | Not started | Unknown |  |  |  | Not started
| Does your organisation have a process for retiring service components securely? | Retiring service components securely | Not started | Unknown |  |  |  | Not started

## Adoption milestones
Secure by Design adoption milestones worksheet This table contains Secure by Design milestones and sub-tasks, with cells to enter data. The table begins in cell A2. Rows 1 and 2 are frozen. The table direction is left to right.
Gaps and actions to help the organisation achieve the Secure by Design implementation milestones |  |  |  | Read the guide to adopting Secure by Design
Secure by Design implementation phase | Type | Unique ID | Description | Assessment status | Identified gaps | Action ID | Proposed actions to address the gap | Status | Owner | Start date | End date | Comments Add notes on gaps and actions
Preparation | Milestone | 1 | Accountability and sponsorship for Secure by Design is formally accepted by your chief digital information officer (CDIO) or equivalent | Not started |  |  |  | Not started
|  | 1.1 | Accountable CDIO or equivalent was appointed. |  |  |  |  | Not started
| Milestone | 2 | Secure by Design champion is appointed | Not started |  |  |  | Not started
|  | 2.1 | Nominate your champions and inform the cross-government Secure by Design team. |  |  |  |  | Not started
|  | 2.2 | Communicate identity of champion and their responsibilities to wider organisation. |  |  |  |  | Not started
| Milestone | 3 | Internal Secure by Design working group is established together with related processes (for example, Terms of Reference (ToR) and cadence of meetings) | Not started |  |  |  | Not started
|  | 3.1 | Discuss which cross functional representation is required to establish a working group with representation across all disciplines including digital, security, commercial, risk, assurance and other teams who will need to support implementation. |  |  |  |  | Not started
|  | 3.2 | Initiate first working group meeting. |  |  |  |  | Not started
|  | 3.3 | Establish regular drumbeat of meetings. |  |  |  |  | Not started
|  | 3.4 | Circulate ToR for review and approval. |  |  |  |  | Not started
|  | 3.5 | Enlarge working group as you engage with stakeholders in your organisation. |  |  |  |  | Not started
| Milestone | 4 | Communication and engagement plan with internal stakeholders is delivered | Not started |  |  |  | Not started
|  | 4.1 | Familiarise yourself Secure by Design communication toolkit. |  |  |  |  | Not started
|  | 4.2 | Ensure CDIO, chief technology officer (CTO) and chief information security officer (CISO) are sighted on Secure by Design and understand their accountabilities. Schedule and run sessions (live or recorded) to introduce Secure by Design and explain stakeholder roles. |  |  |  |  | Not started
|  | 4.3 | Identify and map key internal stakeholders: Include senior leaders, delivery teams, security teams, project management office (PMO), commercial, assurance and risk management teams. |  |  |  |  | Not started
|  | 4.4 | Outline key messages, audiences, objectives, timelines, owners and channels. |  |  |  |  | Not started
|  | 4.5 | Develop communication and engagement plan. Ensure it aligns with your broader Secure by Design transition or implementation plan. |  |  |  |  | Not started
|  | 4.6 | Deliver introductory briefings to key stakeholders: Schedule and run sessions (live or recorded) to introduce Secure by Design and explain stakeholder roles. |  |  |  |  | Not started
|  | 4.7 | Develop initial communication material: Prepare toolkits, FAQs, briefing decks, intranet posts, newsletter articles and templates for team leads. |  |  |  |  | Not started
|  | 4.8 | Tailor communications for each audience: Prepare targeted messages depending on the role and influence of each stakeholder group. |  |  |  |  | Not started
|  | 4.9 | Launch organisation-wide communications: Publish updates via internal channels like newsletters, intranet, webinars, lunch-and-learns, Slack/Teams messages and so on. |  |  |  |  | Not started
|  | 4.1 | Set up feedback mechanisms: Create a way for staff to ask questions, provide feedback or request support (for example, via shared mailboxes, forms or workshops). |  |  |  |  | Not started
| Milestone | 5 | The preparation checklist is complete and the organisation's current Secure by Design state is understood | Not started |  |  |  | Not started
|  | 5.1 | Identify the key people who need to contribute to completing the preparation checklist. |  |  |  |  | Not started
|  | 5.2 | Brief contributors to ensure a shared understanding of Secure by Design principles and expectations. |  |  |  |  | Not started
|  | 5.3 | Complete the preparation checklist collaboratively, capturing the organisation’s current state. |  |  |  |  | Not started
|  | 5.4 | Analyse and confirm the gaps and areas needing improvement. |  |  |  |  | Not started
|  | 5.5 | Prioritise the gaps based on urgency, risk and strategic importance. |  |  |  |  | Not started
|  | 5.6 | Document the prioritised gaps and next steps in the Secure by Design transition plan. |  |  |  |  | Not started
| Milestone | 6 | The scope of Secure by Design implementation is agreed with your CDIO or equivalent in line with Secure by Design policy | Not started |  |  |  | Not started
|  | 6.1 | Review the government Secure by Design policy and any relevant guidance. |  |  |  |  | Not started
|  | 6.2 | Identify the projects, services, teams and processes that fall within the scope of Secure by Design. |  |  |  |  | Not started
|  | 6.3 | Draft a proposed scope for Secure by Design implementation, including any assumptions or exclusions. |  |  |  |  | Not started
|  | 6.4 | Engage with key stakeholders (for example, CTO, CISO, PMO, commercial, delivery leads) to validate the proposed scope. |  |  |  |  | Not started
|  | 6.5 | Present the proposed scope to your CDIO or equivalent for review. |  |  |  |  | Not started
|  | 6.6 | Discuss and refine the scope based on feedback and organisational priorities. |  |  |  |  | Not started
|  | 6.7 | Obtain formal agreement from the CDIO or equivalent on the final scope. |  |  |  |  | Not started
|  | 6.8 | Record and communicate the agreed scope to all relevant teams and include it in the transition plan. |  |  |  |  | Not started
| Milestone | 7 | A transition plan is developed and agreed with CDIO or equivalent | Not started |  |  |  | Not started
|  | 7.1 | Develop a high-level draft of the transition plan based on the organisation’s Secure by Design preparation work. |  |  |  |  | Not started
|  | 7.2 | Build a detailed transition plan aligned to the preparation, transition and operational phases. |  |  |  |  | Not started
|  | 7.3 | Engage key stakeholders (for example, delivery teams, security, PMO, risk teams) to gather input and validate the plan’s activities and timescales. |  |  |  |  | Not started
|  | 7.4 | Refine the transition plan based on stakeholder feedback. |  |  |  |  | Not started
|  | 7.5 | Socialise the plan with senior leaders, governance forums and activity owners to gain early buy-in. |  |  |  |  | Not started
|  | 7.6 | Review the final version of the transition plan with the CDIO (or equivalent senior leader). |  |  |  |  | Not started
|  | 7.7 | Secure formal agreement and sign-off from the CDIO or equivalent. |  |  |  |  | Not started
|  | 7.8 | Confirm the agreed reporting channels and governance forums for monitoring transition plan progress. |  |  |  |  | Not started
| Milestone | 8 | Internal policies and processes are updated with Secure by Design requirements in line with the government Secure by Design policy and approved by your CDIO or equivalent | Not started |  |  |  | Not started
|  | 8.1 | Review internal policies (for example, security, data protection, system architecture) and delivery processes to understand what needs to be updated. |  |  |  |  | Not started
|  | 8.2 | Determine how Secure by Design principles should be incorporated into these policies and processes to ensure alignment with government standards. |  |  |  |  | Not started
|  | 8.3 | Revise policies and operational processes to reflect the Secure by Design requirements, ensuring they meet security, privacy and operational goals. |  |  |  |  | Not started
|  | 8.4 | Work closely with policy owners, legal teams and subject matter experts to ensure the updates are comprehensive and compliant. |  |  |  |  | Not started
|  | 8.5 | Ensure that the updated policies and processes are reviewed and approved by the CDIO or equivalent senior leadership to ensure alignment with the organisation’s strategic objectives. |  |  |  |  | Not started
|  | 8.6 | Prepare internal communication materials to inform all relevant teams and stakeholders about the updated policies and processes. |  |  |  |  | Not started
|  | 8.7 | Ensure that the updated policies and processes are made available across the organisation via appropriate channels (for example, intranet, newsletters, training sessions). |  |  |  |  | Not started
|  | 8.8 | Deliver training and awareness programs to ensure affected teams understand and can effectively implement the updated policies. |  |  |  |  | Not started
|  | 8.9 | Track how well the policies are being adopted within the organisation, gathering feedback and addressing any implementation challenges. |  |  |  |  | Not started
|  | 8.1 | Set a schedule for periodic reviews and updates to ensure ongoing alignment with Secure by Design principles as they evolve. |  |  |  |  | Not started
| Milestone | 9 | Secure by Design is embedded within relevant activities in your PMO or project management practices | Not started |  |  |  | Not started
|  | 9.1 | Review existing PMO or project management processes to identify where Secure by Design can be embedded using the guidance around contracting securely. |  |  |  |  | Not started
|  | 9.2 | Engage with the PMO team to raise awareness about Secure by Design principles and their relevance to project management activities. |  |  |  |  | Not started
|  | 9.3 | Develop and integrate Secure by Design requirements into project initiation and planning phases (for example, risk assessments, project charters). |  |  |  |  | Not started
|  | 9.4 | Align project delivery stages with Secure by Design requirements, ensuring each stage addresses security concerns. |  |  |  |  | Not started
|  | 9.5 | Include Secure by Design checkpoints in governance and project review meetings to ensure ongoing compliance. |  |  |  |  | Not started
|  | 9.6 | Create templates and tools (for example, project risk logs, security checklists) that incorporate Secure by Design principles for use in project management activities. |  |  |  |  | Not started
|  | 9.7 | Train project managers and relevant stakeholders on how to incorporate Secure by Design throughout the project life cycle. |  |  |  |  | Not started
|  | 9.8 | Monitor project progress to ensure that Secure by Design activities are being executed as planned and resolve any blockers or gaps. |  |  |  |  | Not started
|  | 9.9 | Report on Secure by Design progress in regular PMO or project governance meetings to ensure alignment with overarching organisational goals. |  |  |  |  | Not started
Transition | Milestone | 10 | One or more projects to test the Secure by Design self assessment tracker are identified and have accepted their obligations | Not started |  |  |  | Not started
|  | 10.1 | Identify upcoming or live digital/technology projects that are suitable for piloting the self-assessment tracker. |  |  |  |  | Not started
|  | 10.2 | Engage with project SROs, delivery managers and security leads to explain the purpose and expectations of the pilot. |  |  |  |  | Not started
|  | 10.3 | Provide projects with a briefing on Secure by Design principles and how the self-assessment tracker supports them. |  |  |  |  | Not started
|  | 10.4 | Secure agreement from project teams to participate in the pilot and formally confirm their commitment. |  |  |  |  | Not started
|  | 10.5 | Clarify the support and resources that will be available to pilot projects during the testing phase. |  |  |  |  | Not started
|  | 10.6 | Define clear pilot expectations, including milestones, feedback points and timelines for using the tracker. |  |  |  |  | Not started
|  | 10.7 | Assign a point of contact within the Secure by Design implementation team for pilot project support. |  |  |  |  | Not started
|  | 10.8 | Ensure participating projects understand their obligation to complete the tracker and provide feedback on its use. |  |  |  |  | Not started
|  | 10.9 | Test the self assessment tracker. |  |  |  |  | Not started
|  | 10.1 | Schedule regular check-ins with pilot projects to monitor progress and capture early feedback. |  |  |  |  | Not started
| Milestone | 11 | Feedback from pilot projects is captured, reviewed and reflected in your transition plan | Not started |  |  |  | Not started
|  | 11.1 | Select and confirm the pilot projects that will be used to test the Secure by Design implementation process. |  |  |  |  | Not started
|  | 11.2 | Gather detailed feedback from teams involved in the pilot projects, including lessons learned, challenges faced and suggestions for improvement. |  |  |  |  | Not started
|  | 11.3 | Review the feedback collected from the pilot projects, identifying recurring themes, key issues and potential improvements. |  |  |  |  | Not started
|  | 11.4 | Evaluate how the feedback affects the current transition plan and Secure by Design implementation strategy. |  |  |  |  | Not started
|  | 11.5 | Incorporate feedback and lessons learned from the pilot projects into the transition plan, adjusting timelines, activities or responsibilities as necessary. |  |  |  |  | Not started
|  | 11.6 | Ensure that key stakeholders are informed of the changes made to the transition plan based on pilot feedback. |  |  |  |  | Not started
|  | 11.7 | Set up mechanisms to track the implementation of changes derived from pilot feedback and ensure continuous improvement throughout the delivery process. |  |  |  |  | Not started
|  | 11.8 | Continue monitoring the progress of the pilot projects to ensure that the adjustments made to the transition plan are delivering the desired results. |  |  |  |  | Not started
| Milestone | 12 | The transition plan is now an operational plan and the organisation is ready to go live with Secure by Design | Not started |  |  |  | Not started
|  | 12.1 | Agree the initial scope for a Secure by Design playbook or checklist for your organisation. |  |  |  |  | Not started
|  | 12.2 | Develop playbook or checklist for your organisation or build Secure by Design into an existing playbook (for example, a digital delivery playbook). |  |  |  |  | Not started
|  | 12.3 | Produce an artefact that clearly shows what needs to be done by whom around Secure by Design at each stage of digital delivery, including key points in the gate process. |  |  |  |  | Not started
|  | 12.4 | Brief delivery, PMO, security and other relevant teams on the playbook. |  |  |  |  | Not started
|  | 12.5 | Track use of the playbook and get feedback. |  |  |  |  | Not started
|  | 12.6 | Update the playbook as and when required. |  |  |  |  | Not started
|  | 12.7 | Embed processes into business as usual (BAU). |  |  |  |  | Not started
|  | 12.8 | Check projects are passing through the spend control process smoothly. |  |  |  |  | Not started
|  | 12.9 | Track use of the self assessment tracker within projects. |  |  |  |  | Not started
|  | 12.1 | Ensure there is a strong feedback loop for teams and individuals to report their findings using the Secure by Design process and materials. |  |  |  |  | Not started
|  | 12.11 | Develop a backlog of continuous improvement ideas and suggestions to further enhance the Secure by Design offering. |  |  |  |  | Not started
|  | 12.12 | Ensure there is a clear reporting mechanism to assess Secure by Design compliance and highlight any corrective actions. |  |  |  |  | Not started
|  | 12.13 | Ensure there is an ongoing forum where projects and teams can seek guidance and assistance. |  |  |  |  | Not started
|  | 12.14 | Ensure lessons learned are shared widely across the organisation and encourage best practice and knowledge transfer. |  |  |  |  | Not started
| Milestone | 13 | Secure by Design progress is shared regularly with internal teams and senior leaders | Not started |  |  |  | Not started
|  | 13.1 | Add Secure by Design updates to regular governance meetings agendas, ensuring senior leaders are kept informed of progress, risks and blockers. |  |  |  |  | Not started
|  | 13.2 | Share the output of Secure by Design Working Group sessions, including key decisions, actions and milestones, to keep teams aligned. |  |  |  |  | Not started
|  | 13.3 | Provide regular status reports to senior leadership, highlighting progress against the Secure by Design plan, any challenges faced and mitigation strategies. |  |  |  |  | Not started
|  | 13.4 | Maintain an open feedback loop with internal teams, allowing them to voice concerns or suggestions for improvement in the Secure by Design implementation. |  |  |  |  | Not started
|  | 13.5 | Ensure key stakeholders are aware of Secure by Design milestones and actions, through email updates, dashboards or dedicated channels. |  |  |  |  | Not started
|  | 13.6 | Review Secure by Design progress at key decision points and use that to inform strategic decisions related to digital delivery and security. |  |  |  |  | Not started
Operation | Milestone | 14 | Your indicative go-live date is agreed | Not started |  |  |  | Not started
|  | 14.1 | Coordinate with key stakeholders (for example, project team, CDIO, business units, vendors and service providers) to ensure alignment on the go-live date. |  |  |  |  | Not started
|  | 14.2 | Get approval from the CDIO. |  |  |  |  | Not started
|  | 14.3 | Schedule a review meeting to finalise the go-live date, assess potential risks and make any adjustments if needed. |  |  |  |  | Not started
|  | 14.4 | Set up a contingency plan in case of delays or issues that might affect the go-live date, ensuring that risk management measures are in place. |  |  |  |  | Not started

## Release notes
Release notes worksheet. This table contains release date, version number and changes. The table begins in cell A2. Rows 1 and 2 are frozen. The table direction is left to right.
Release date | Version number | Changes
Sunday 9 February 2025 | Alpha v2.1 | • Removed mention of GDS to reflect new organisational structure • Minor style correction
Wednesday 7 May 2025 | Alpha v2.0 | • Updated adoption milestones to align with success metrics • Accessibility improvements, including increased font size, index worksheet for navigation, worksheet descriptions, accessible colour contrast, left-aligned text content, unmerged cells and so on
Not published on website | Alpha v1.0